## tf-2017
FDP Form 6-Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
For the 1st Quarter, CY 2017
Province, City or Municipality: North Cotabato, Matalam
| Programs or Projects | Location | Total | Date Started | Target | Project Status |  | No. of
|  |  | Cost |  | Completion | % of | Total Cost | Extensions, | Remarks
[5 empty] | Date | Completion | Incurred to Date | if any
1 | First & Second Quarter Financial Assistance/Stipend Social Pensioners | Matalam | 3049500 | 03/2017 |  |  | 3049500 |  | On Going
2 | Construction of Solar Drier (DA-RFO-XII BUB) | New Bugasong | 250000 | 03/2017 |  |  | 0 |  | On Going
3 | Construction of Solar Drier (DA-RFO-XII BUB) | Salvacion | 250000 | 03/2017 |  |  | 0 |  | On Going
| Total |  | 3549500 |  |  |  | 3049500
We hereby certify that we have reciewed the contents and hereby attest to
the veracity and correctness of the data or information contained in this
document.
| LERIO D. MIGUEL, CPA | [5 empty] | CHERYL V. CATAMCO, RN
| Municipal Accountant | [5 empty] | Municipal Mayor

## 20%-2017
FDP Form 7-20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION CY-2017
For the 1st Quarter, CY 2017
Province, City or Municipality: North Cotabato, Matalam
| Program or Project | Location | Total | Date Started | Target | Project Status |  | No. of
|  |  | Cost |  | Completion | % of | Total Cost | Extensions, | Remarks
[5 empty] | Date | Completion | Incurred to Date | if any
A | SOCIAL DEVELOPMENT
1 | Expansion of Bgy Bato Water System (Pagangan-Proper) |  | 300000 |  |  | 100% | 298330
2 | Completion of New Bugasong Health Center |  | 150000 |  |  |  | 0
3 | Completion of Dalapitan Health Center |  | 100000 |  |  |  | 0
4 | Const. of New Alimodian Day Care Center |  | 250000 |  |  |  | 0
5 | Aid to Bangbang Water System (Provision of P.E. pipe) |  | 50000 |  |  |  | 0
6 | Aid to const. of Taguranao Elevated Reservoir |  | 500000 |  |  |  | 0
7 | Aid to const. of New Abra elevated water tank |  | 275000 |  |  |  | 0
8 | Renovation of Manupal Day Care Center (Pk. 3 and &) |  | 100000 |  |  |  | 0
9 | Renovation of Kilada Health Center/Birthing room |  | 150000 |  |  |  | 0
10 | Const. of Kibia(Napasaan) Water Reservoir |  | 160000 |  |  |  | 0
11 | Const. of Kibia Multi-Purpose Covered Hall Flooring |  | 160000 |  |  |  | 0
12 | Completion of Kilada Day Care Center (Sitio Biao and Kinudal) |  | 100000 |  |  |  | 0
13 | Aid to completion of Sitio Maligaya Day Care Center |  | 20000 |  |  |  | 0
14 | Completion of Pinamaton Day Care Center |  | 70000 |  |  |  | 0
15 | Const. of Multi-Purpose covered court flooring |  | 160000 |  |  |  | 0
B | ECONOMIC DEVELOPMENT (Infra-support)
1 | Rehab of Pinamaton-Lamanan road |  | 200000 |  |  |  | 0
2 | Rehab of Arakan-Kulog road |  | 200000 |  |  |  | 0
3 | C. Malamote-F. Valdevieso road opening |  | 200000 |  |  |  | 0
4 | Rehab of Minamaing-Tagaytay-Calura road |  | 100000 |  |  |  | 0
5 | Rehab of Sarayan-Maiwag-Pk 13 road |  | 200000 |  |  |  | 0
6 | Rehab of Taculen-Dalapitan-L.Malamote road |  | 50000 |  |  |  | 0
7 | Natutungan-Marubo road opening |  | 75000 |  |  |  | 0
8 | Rehab of Lampayan-Panipasan road |  | 75000 |  |  |  | 0
9 | Rehab of Sta.Maria-Calura road |  | 200000 |  |  |  | 0
10 | Rehab of Sitio Dimomoyog-Kibia road |  | 200000 |  |  |  | 0
11 | Rehab of Estado-Mill site-Esmar-Mercado road |  | 150000 |  |  |  | 0
12 | Const. of Kibia Solar Drier (Purok 18) |  | 250000 |  |  |  | 0
13 | Concreting of Municipal/Barangay roads |  | 16224865.2 |  |  |  | 0
14 | Counterpart Funds for Local, Nat'l. & Foreign Funded Projects |  | 4600000 |  |  |  | 0
15 | Rehab of Tigbawan-Bugtong Bukid road (Lampayan) |  | 176000 |  |  |  | 0
16 | Const. of Purok 5 Solar Drier, Manubuan |  | 250000 |  |  |  | 0
17 | Rehab of Taculen-L.Malamote road, Taculen |  | 75000 |  |  |  | 0
18 | Rehab of Upper F. Valdevieso-C. Malamote road |  | 100000 |  |  |  | 0
19 | Const. of Solar Drier, Bgy. Hall Compound, Taguranao |  | 250000 |  |  |  | 0
C | ENVIRONMENTAL MANAGEMENT(9000)
1 | Provision of Equipment and Machineries for the Operation of |  | 15000000 |  |  |  | 0
Sanitary Land Fill of the Municipality
| Total |  | 41120865.2 |  |  |  | 298330
We hereby certify that we have reciewed the contents and hereby attest to
the veracity and correctness of the data or information contained in this
document.
| LERIO D. MIGUEL, CPA | [5 empty] | CHERYL V. CATAMCO, RN
| Municipal Accountant | [5 empty] | Municipal Mayor

## CF-2017
FDP Form 9-Statement of Cash Flows
(COA Form)
STATEMENT OF CASH FLOWS
As of March 31, 2017
Province, City or Municipality: North Cotabato, Matalam
Cash Flows from Operating Activities:
Cash Inflows:
| Collections from Taxpayers | 5786151.31
| Share from Internal Revenue Collections | 46761880
| Receipts from Business/Service Income | 2515549.61
| Interest Income | 0
| Other Receipts | 44600555.12
| Total Cash Inflow | 99664136.04
Cash Outflows:
Payments -
| To suppliers/creditors | 33813055.04
| To Employees | 13493585.43
| Total Cash Outflow | 47306640.47
| Net Cash from Operating Activities |  | 52357495.57
Cash Flows from Investing Activities:
Cash Inflows:
| From Sale of Property, Plant and Equipment | 0
| From Sale of Debt Securities of Other Entities | 0
| From Coll. of Principal on Loans to Other Entities | 0
| Total Cash Inflows | 0
Cash Outflows:
| To Purchase Property, Plant and Equipment | 0
| To Purchase Debt Securities of Other Entities | 0
| Total Cash Outflow | 0
| Net Cash from Investing Activities: |  | 0
Cash Flows from Financing Activities
Cash Inflows:
| From Issuance of Debt Securities | 0
| From Acquisition of Loan | 0
| Total Cash Outflow | 0
Cash Outflows:
Bank Charges on Dormant Accounts
| Payment of Loan Amortization | 0
| Total Cash Outflow | 0
| Net Cash from Financing Activities | 0
Net Increase in Cash |  |  | 52357495.57
Cash at Beginning of the Period |  |  | 199697220.74
Cash at the End of the Period |  |  | 252054716.31
CERTIFIED CORRECT:
LERIO D. MIGUEL, CPA
Municipal Accountant

## sef-util. -2017
FDP Form 11-SEF Utilization
(SEF Budget Accountability Form No. 1)
SEF UTILIZATION
For the Quarter Ending March 31, 2017
Province/City/Municipality : North Cotabato, Matalam
Receipt from SEF |  | Php | 1376913.86
Less: | DISBURSEMENTS (broken down by expense
class and by object of expenditure)
Personal Services
| Salaries & Wages - Casual |  | 0
Maintenance and Other Operating Expenses
| Gasoline, Oil & Lubricant |  | 6698.74
| Repair & Maint.-School Building |  | 0
| Donations |  | 0
| Depreciations |  | 0
| Capital Outlay |  | 0
| Financial Expenses |  | 0
Sub-Total |  |  | 6698.74
Balance |  | Php | 1370215.12
We hereby certify that we have reviewed
the contents and hereby attest toi the veracity
and correctness of the data or information
contained in this documents.
LERIO D. MIGUEL, CPA
Municipal Accountant
CHERYL V. CATAMCO, RN
LCE, Chairman, LSB

## debt-2017
FDP Form 2-Statement of Debt Service
(DBM-LBP Form No. 6)
STATEMENT OF DEBT SERVICE
As of March 31, 2017
Province, City or Municipality: North Cotabato, Matalam
FUND/SPECIAL ACCOUNT: General Fund
| Date Contarcted |  |  |  | Previous Payment |  |  | Amount Due |  | Balance of the Principal
Creditor |  | Term | Principal Amount |  | Made |  |  | (Budget Year)
[5 empty] | (5) |  |  | (6)
(1) | (2) | (3) | (4) | Principal | Interest | Total | Principal | Interest | Total | (7)
| Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
We hereby certify that we reviewed the contents and hereby attest to
the veracity and correctness of the data or information contained in this
documents
|  |  | LERIO D. MIGUEL, CPA |  |  |  | CHERYL V. CATAMCO, RN
|  |  | Municipal Accountant |  |  |  | Municipal Mayor
None

## LDRRM
FDP Form 8- Local Disaster Risk Reduction and Management Fund Utilization
(COA Form)
LOCAL DISASTER RISK REDUCTION AND MANAGEMENT FUND UTILIZATION
For the 1st Quarter CY 2017
Province, City or Municipality:NORTH COTABATO, MATALAM
LDRRMF
PARTICULARS |  | QUICK RESPONSE | MITIGATION FUND | NDRRMF | FROM OTHER | FROM OTHER | TOTAL
|  | FUND (QRF) |  |  | LGUs | SOURCES
|  | 30% | 70%
A. Sources of Funds
Current Appropriations | 2017 | 510129.6 | 1190302.4 |  |  |  | 1700432
Continuing Appropriations | 2016 | 2142919.2 | 5872715.25 | - | - | - | 8015634.45
| 2015 | 381226.17 | 2363895.08 | - | - | - | 2745121.25
| 2014 | 0.00 | 1769229.56 | - | - | - | 1769229.56
| 2013 | 0.00 | 2377664.59 | - | - | - | 2377664.59
| 2012 | 0.00 | 347793.35 | - | - | - | 347793.35
Initial Deposit |  |  | 10000 |  |  |  | 10000
Interest Income |  |  | 9169.63 |  |  |  | 9169.63
| - | - | - | - | - | - | -
Previous Year's | - | - | - | - | - | - | -
Appropriations transferred to the Special Trust Fund | - | - | - | - | - | - | -
Transfers/Grants | - | - | - | - | - | - | -
Total Funds Available | - | 3034274.97 | 13940769.86 | - | - | - | 16975044.83
B. Utilization | - | - | - | - | - | - | -
Medicines | - | - | - | - | - | - | -
Food Supplies/Non Food Supplies | (2016-70%) | - | 102595 |  | - | - | 102595
| (2015-70%) | - | 13025 | - | - | - | 13025
| - | - | - | - | - | - | -
| - | - | - | - | - | - | -
Repair of Evacuation Center | - | - | - | - | - | - | -
Trainings(snacks) | - | - | - | - | - | - | -
Construction of Evacuation Center | - | - | - | - | - | - | -
Equipment | - | - | - | - | - | - | -
FLOOD CONTROL PROJECTS: CONST.OF DRAINAGE CANAL @ MANUAL L. QUEZON | (2014-70%) | - | 297770 | - | - | - | 297770
| - | - | - | - | - | - | -
| - | - | - | - | - | - | -
| - | - | - | - | - | - | -
| - | - | - | - | - | - | -
| - | - | - | - | - | - | -
| - | - | - | - | - | - | -
| - | - | - | - | - | - | -
Transfers to the LGUs | - | - | - | - | - | - | -
Total Utilization |  | - | 413390 | - | - | - | 413390
Unutilized Balance |  | 3034274.97 | 13527379.86 | - | - | - | 16561654.83
I hereby certify that I have reviewed the contents and hereby attest to the veracity and correctness of data or information contained in this document.
LERIO D. MIGUEL, CPA
Municipal Accountant

## Cash Advance
UNLIQUIDATED CASH ADVANCES
As of March 31, 2017
Name of Debtor | Amount Balance | Date Granted | Purpose | Amount Due
|  |  |  | Current |  |  | Past Due
|  |  |  | Less than 30 days | 31-90 days | 91-365 days | Over 1 year | Over 2 years | 3 years and above
Oscar M. Valdevieso | 500000 | 10/20/11 | CIF-Submitted to CO,Manila | [5 empty] | 500000
Oscar M. Valdevieso | 750000 | 09/06/12 | CIF-Submitted to CO,Manila | [5 empty] | 750000
Oscar M. Valdevieso | 500000 | 07/30/13 | CIF-Submitted to CO,Manila | [5 empty] | 500000
Oscar M. Valdevieso | 400000 | 12/10/13 | CIF-Submitted to CO,Manila | [5 empty] | 400000
Basilisa T. Campaña | 1000 | 10/12/15 | Travel |  |  |  | 1000
Rogelio M. Cristobal | 26420 | 02/9/17 | Travel |  | 26420
Trinidad T. Butardo | 23875 | 02/20/17 | Travel |  | 23875
Julieta C. Valdez | 23875 | 02/20/17 | Travel |  | 23875
Clarifie Lagazo | 19730 | 02/27/17 | Travel |  | 19730
Christopher M. Barraca | 25844 | 02/27/17 | Travel |  | 25844
Mylyn S. Babol | 25044 | 02/27/17 | Travel |  | 25044
Trinidad T. Butardo | 3000 | 03/17/17 | Travel | 3000
Rolando M. Bernardino | 10160 | 03/17/17 | Travel | 10160
Wilfredo V. Juloya, Jr. | 15942.44 | 03/17/17 | Travel | 15942.44
Orlando M. Versola | 10160 | 03/17/17 | Travel | 10160
Nazareth Toledo | 10160 | 03/17/17 | Travel | 10160
Virgilio M. Fuerte | 10160 | 03/17/17 | Travel | 10160
Aleli A. Locsin | 10160 | 03/17/17 | Travel | 10160
Rhemia G. Guianan | 10160 | 03/17/17 | Travel | 10160
Hargie S. Borra | 6860 | 03/17/17 | Travel | 6860
Federico L. Dinsay | 10100 | 03/20/17 | Travel | 10100
Jocelyn Cupo | 10040 | 03/21/17 | Travel | 10040
Edgardo E. Seguerra | 7840 | 03/20/17 | Travel | 7840
Cheryl V. Catamco | 6000 | 03/20/17 | Travel | 6000
Rhea A. Alcueba | 6000 | 03/20/17 | Travel | 6000
Marlyn F. Samson | 10160 | 03/17/17 | Travel | 10160
Wilma J. Ma-aya | 10160 | 03/17/17 | Travel | 10160
Doris B. Torres | 10160 | 03/17/17 | Travel | 10160
Samuel F. Faeldonia | 4660 | 03/17/17 | Travel | 4660
Rosevilla R. Cumaling | 10160 | 03/17/17 | Travel | 10160
Total | 2467830.44 |  |  | 172042.44 | 144788 | 0 | 1000 | 0 | 2150000
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
| LERIO D. MEGUEL, CPA | [5 empty] | CHERYL V. CATAMCO, RN
| Municipal Accountant | [5 empty] | Municipal Mayor