## tf-2017
FDP Form 6-Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
For the 2nd Quarter, CY 2017
Province, City or Municipality: North Cotabato, Matalam
| Programs or Projects | Location | Total | Date Started | Target | Project Status |  | No. of
|  |  | Cost |  | Completion | % of | Total Cost | Extensions, | Remarks
[5 empty] | Date | Completion | Incurred to Date | if any
1 | First & Second Quarter Financial Assistance/Stipend Social Pensioners | Matalam | 3049500 | 03/2017 |  |  | 3049500 |  | On Going
2 | Construction of Solar Drier (DA-RFO-XII BUB) | New Bugasong | 250000 | 03/2017 |  |  | 125000 |  | On Going
3 | Construction of Solar Drier (DA-RFO-XII BUB) | Salvacion | 250000 | 03/2017 |  |  | 125000 |  | On Going
4 | Construction of PWS | New Bugasong | 1250000 | 03/2017 |  |  | 1244993.73 |  | Completed
5 | Assistance to Individuals & Families in Crisis Situation | Matalam | 500000 | 03/2017 |  |  | 50500 |  | On Going
6 | Construction of PWS | Taguranao | 1130000 | 03/2017 |  |  | 1126997 |  | Completed
7 | Construction of PWS | Dapaitan | 1000000 | 06/2017 |  |  | 696927.56 |  | On Going
8 | Construction of PWS | C. Malamote | 1000000 | 06/2017 |  |  | 813157.76 |  | On Going
9 | Agricultural Production | Kilada | 987500 | 06/2017 |  |  | 19112.5 |  | On Going
10 | Agricultural Production | Marbel | 987500 | 06/2017 |  |  | 0 |  | On Going
11 | Agricultural Production | Natutungan | 987500 | 06/2017 |  |  | 19112.5 |  | On Going
| Total |  | 11392000 |  |  |  | 7270301.05
We hereby certify that we have reciewed the contents and hereby attest to
the veracity and correctness of the data or information contained in this
document.
| LERIO D. MIGUEL, CPA | [5 empty] | CHERYL V. CATAMCO, RN
| Municipal Accountant | [5 empty] | Municipal Mayor