## Sheet1
FDP Form 6-Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
For the 4th Quarter, CY 2016
Province, City or Municipality: North Cotabato, Matalam
| Programs or Projects | Location | Total | Date Started | Target | Project Status |  | No. of
|  |  | Cost |  | Completion | % of | Total Cost | Extensions, | Remarks
[5 empty] | Date | Completion | Incurred to Date | if any
1 | First & Second Quarter Financial Assistance/Stipend Social Pensioners | Matalam | 8757000 | 02/2016 | 2016-09-30 | 100% | 8757000 |  | Fully Implemented
2 | Construction Evacuation Center | Poblacion | 2100000 | 01/2016 | 6/13/2016 | 100% | 1589362.31 |  | Fully Implemented
3 | Construction of DRRM Flood Control | L. Malamote | 800000 | 02/2016 | 5/24/2016 | 100% | 720038.24 |  | Fully Implemented
4 | Const. of Potable Water Supply | Taguranao | 1126997 | 03/2016 |  | 15% | 169049.55 |  | On-going
5 | Const. of Potable Water Supply | Marbel | 1136000 | 03/2016 |  | 3.521% | 40000 |  | On-going
6 | Const. of Potable Water Supply | N. Alimodian | 2165000 | 03/2016 |  | 87.85% | 1855310.54 |  | On-going
7 | Const. of Potable Water Supply | Natutungan | 3000000 | 04/2016 |  | 62.04% | 1861341.71 |  | On-going
8 | Const. of Potable Water Supply | New Bugasong | 1000000 |  |  | 10% | 96000 |  | On-going
9 | Const. of Potable Water Supply | Dalapitan | 1000000 |  |  | 9.6% | 96000 |  | On-going
10 | Const. of Potable Water Supply | Taguranao | 1000000 | 06/30/16 |  | 78.89% | 788869.31 |  | On-going
11 | Const. of Potable Water Supply | C. Malamote | 1000000 |  |  | 10% | 96000 |  | On-going
12 | Const. of Potable Water Supply | Latagan | 1000000 | 09/06/16 |  | 29.97% | 299704.37 |  | On-going
13 | Integrated Community Food Production | Matalam | 1680000 | 05/2016 |  | 19.89% | 334201 |  | On-going
14 | Farm Implements/Tools | Matalam | 600000 | 12/2016 | 12/31/2016 | 100% | 592640 |  | Fully Implemented
| Total |  | 26364997 |  |  |  | 17295517.03
We hereby certify that we have reciewed the contents and hereby attest to
the veracity and correctness of the data or information contained in this
document.
| LERIO D. MIGUEL, CPA | [5 empty] | CHERYL V. CATAMCO, RN
| Municipal Accountant | [5 empty] | Municipal Mayor