## tf-2017
FDP Form 6-Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
For the 4th Quarter, CY 2017
Province, City or Municipality: North Cotabato, Matalam
| Programs or Projects | Location | Total | Date Started | Target | Project Status |  | No. of
|  |  | Cost |  | Completion | % of | Total Cost | Extensions, | Remarks
[5 empty] | Date | Completion | Incurred to Date | if any
1 | First & Second Quarter Financial Assistance/Stipend Social Pensioners | Matalam | 17244000 | 03/2017 |  |  | 17244000 |  | Completed
2 | Construction of Solar Drier (DA-RFO-XII BUB) | New Bugasong | 250000 | 03/2017 |  |  | 125000 |  | On Going
3 | Construction of Solar Drier (DA-RFO-XII BUB) | Salvacion | 250000 | 03/2017 |  |  | 125000 |  | On Going
4 | Construction of PWS | New Bugasong | 1250000 | 03/2017 |  |  | 1244993.73 |  | Completed
5 | Assistance to Individuals & Families in Crisis Situation | Matalam | 500000 | 03/2017 |  |  | 322500 |  | On Going
6 | Construction of PWS | Taguranao | 2130000 | 03/2017 |  |  | 1126997 |  | Completed
7 | Construction of PWS | Dapaitan | 1250000 | 06/2017 |  |  | 1245721.58 |  | Completed
8 | Construction of PWS | C. Malamote | 1250000 | 06/2017 |  |  | 1245725.24 |  | Completed
9 | Construction of PWS | N. Bugasong | 1250000 | 09/2017 |  |  | 1244993.73 |  | Completed
10 | Construction of PWS | Taculen | 1250000 | 09/2017 |  |  | 1244920.95 |  | Completed
11 | Agricultural Production | Kilada | 1149500 | 06/2017 |  |  | 1099864.5 |  | Completed
12 | Agricultural Production | Marbel | 1137500 | 06/2017 |  |  | 1084903 |  | Completed
13 | Agricultural Production | Natutungan | 1149500 | 06/2017 |  |  | 1100722.5 |  | Completed
14 | ECCD Kit/Learning Materials | Matalam | 1000000 | 09/2017 |  |  | 1000000 |  | Completed
15 | Skills Training on Goat Production | Matalam | 1000000 | 09/2017 |  |  | 1000000 |  | Completed
16 | Concreting of New Abra-Kabulacan Road | Matalam | 13522000 | 09/2017 |  |  | 8686722.2 |  | On Going
17 | BNS Travelling | Matalam | 61320 | 07/2017 |  |  | 61320 |  | Completed
18 | Supplemental Feeding Program | Matalam | 3366000 | 07/2017 |  |  | 2618000 |  | On Going
19 | Livelihood Projects (DA) | Matalam | 960000 | 09/2017 |  |  | 960000 |  | Completed
20 | Trading Post | Matalam | 1000000 | 09/2017 |  |  | 1000000 |  | Completed
21 | Multi-purpose Drying Pavement | Matalam | 1000000 |  |  |  | 999999.96 |  | Completed
22 | Community Based Management System | Matalam | 2000000 |  |  |  | 1521590.4 |  | On Going
| Total |  | 53969820 |  |  |  | 46302974.79
We hereby certify that we have reciewed the contents and hereby attest to
the veracity and correctness of the data or information contained in this
document.
| LERIO D. MIGUEL, CPA | [5 empty] | CHERYL V. CATAMCO, RN
| Municipal Accountant | [5 empty] | Municipal Mayor