## 20%-2017
FDP Form 7-20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION CY-2017
For the 4th Quarter, CY 2017
Province, City or Municipality: North Cotabato, Matalam
| Program or Project | Location | Total | Date Started | Target | Project Status |  | No. of
|  |  | Cost |  | Completion | % of | Total Cost | Extensions, | Remarks
[5 empty] | Date | Completion | Incurred to Date | if any
A | SOCIAL DEVELOPMENT
1 | Expansion of Bgy Bato Water System (Pagangan-Proper) |  | 300000 |  |  | 100% | 298330
2 | Completion of New Bugasong Health Center |  | 150000 |  |  | 100% | 149383.5
3 | Completion of Dalapitan Health Center |  | 100000 |  |  |  | 0
4 | Const. of New Alimodian Day Care Center |  | 250000 |  |  | 100% | 232629.6
5 | Aid to Bangbang Water System (Provision of P.E. pipe) |  | 50000 |  |  | 100% | 49966
6 | Aid to const. of Taguranao Elevated Reservoir |  | 500000 |  |  |  | 0
7 | Aid to const. of New Abra elevated water tank |  | 275000 |  |  | 75% | 204573.7
8 | Renovation of Manupal Day Care Center (Pk. 3 and 5) |  | 100000 |  |  | 100% | 77790.27
9 | Renovation of Kilada Health Center/Birthing room |  | 150000 |  |  |  | 0
10 | Const. of Kibia(Napasaan) Water Reservoir |  | 160000 |  |  |  | 0
11 | Const. of Kibia Multi-Purpose Covered Hall Flooring |  | 160000 |  |  | 100% | 159078.75
12 | Completion of Kilada Day Care Center (Sitio Biao and Kinudal) |  | 100000 |  |  |  | 0
13 | Aid to completion of Sitio Maligaya Day Care Center |  | 20000 |  |  |  | 0
14 | Completion of Pinamaton Day Care Center |  | 70000 |  |  | 100% | 55902.44
15 | Const. of Multi-Purpose covered court flooring |  | 160000 |  |  |  | 0
B | ECONOMIC DEVELOPMENT (Infra-support)
1 | Rehab of Pinamaton-Lamanan road |  | 200000 |  |  | 100% | 199730.7
2 | Rehab of Arakan-Kulog road |  | 200000 |  |  | 100% | 184889.25
3 | C. Malamote-F. Valdevieso road opening |  | 200000 |  |  | 100% | 198920.5
4 | Rehab of Minamaing-Tagaytay-Calura road |  | 100000 |  |  |  | 0
5 | Rehab of Sarayan-Maiwag-Pk 13 road |  | 200000 |  |  | 100% | 185643.9
6 | Rehab of Taculen-Dalapitan-L.Malamote road |  | 50000 |  |  |  | 0
7 | Natutungan-Marubo road opening |  | 75000 |  |  |  | 0
8 | Rehab of Lampayan-Panipasan road |  | 75000 |  |  |  | 0
9 | Rehab of Sta.Maria-Calura road |  | 200000 |  |  | 100% | 199753.9
10 | Rehab of Sitio Dimomoyog-Kibia road |  | 200000 |  |  | 90% | 172324.6
11 | Rehab of Estado-Mill site-Esmar-Mercado road |  | 150000 |  |  | 100% | 149788.1
12 | Const. of Kibia Solar Drier (Purok 18) |  | 250000 |  |  | 85% | 203517.75
13 | Concreting of Municipal/Barangay roads |  | 16224865.2 |  |  | 60% | 8376501.5
14 | Counterpart Funds for Local, Nat'l. & Foreign Funded Projects |  | 4600000 |  |  | 21.74% | 1000000
15 | Rehab of Tigbawan-Bugtong Bukid road (Lampayan) |  | 176000 |  |  |  | 0
16 | Const. of Purok 5 Solar Drier, Manubuan |  | 250000 |  |  | 85% | 204363
17 | Rehab of Taculen-L.Malamote road, Taculen |  | 75000 |  |  |  | 0
18 | Rehab of Upper F. Valdevieso-C. Malamote road |  | 100000 |  |  | 100% | 94221.3
19 | Const. of Solar Drier, Bgy. Hall Compound, Taguranao |  | 250000 |  |  | 95% | 202825
C | ENVIRONMENTAL MANAGEMENT(9000)
1 | Provision of Equipment and Machineries for the Operation of |  | 15000000 |  |  | 100% | 14290000
Sanitary Land Fill of the Municipality
| Total |  | 41120865.2 |  |  |  | 26890133.76
We hereby certify that we have reciewed the contents and hereby attest to
the veracity and correctness of the data or information contained in this
document.
| LERIO D. MIGUEL, CPA | [5 empty] | CHERYL V. CATAMCO, RN
| Municipal Accountant | [5 empty] | Municipal Mayor