## tf-2018
FDP Form 6-Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
For the 3rd Quarter, CY 2018
Province, City or Municipality: North Cotabato, Matalam
| Programs or Projects | Location | Total | Date Started | Target | Project Status |  | No. of
|  |  | Cost |  | Completion | % of | Total Cost | Extensions, | Remarks
[5 empty] | Date | Completion | Incurred to Date | if any
1 | Construction of Potable Water System | Matalam | 750000 |  | 02/28/18 | 100% | 750000 |  | Completed
2 | DILEEP - 361 Beneficiaries | Matalam | 2963335 |  |  |  | 0 |  | On Going
3 | 4,444 Social Pensioners - 1st Quarter 2018 | Matalam | 6666000 |  |  | 100% | 6666660 |  | Completed
4 | 4,444 Social Pensioners - 2nd Quarter 2018 | Matalam | 6666000 |  |  | 100% | 6666660 |  | Completed
5 | Materials Recovery Facility | Matalam | 300000 |  |  | 50% | 150000 |  | On Going
6 | Construction of Solar Drier | Kibudoc | 300000 |  |  | 50% | 150000 |  | On Going
7 | Construction of Solar Drier | Lampayan | 300000 |  |  | 50% | 150000 |  | On Going
8 | Construction of Solar Drier | L. Malamote | 300000 |  |  | 50% | 150000 |  | On Going
9 | Construction of Solar Drier | Manubuan | 300000 |  |  | 50% | 150000 |  | On Going
10 | Travelling Rice Mill | Kibia | 300000 |  |  | 100% | 240000 |  | Completed
11 | Travelling Rice Mill | Manupal | 300000 |  |  | 100% | 240000 |  | Completed
12 | Travelling Rice Mill | Marbel | 300000 |  |  | 100% | 240000 |  | Completed
| Total |  | 19445335 |  |  |  | 15553320
We hereby certify that we have reciewed the contents and hereby attest to
the veracity and correctness of the data or information contained in this
document.
| LERIO D. MIGUEL, CPA | [5 empty] | CHERYL V. CATAMCO, RN
| Municipal Accountant | [5 empty] | Municipal Mayor