## 20%-2018
FDP Form 7-20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION CY-2018
For the 3rd Quarter, CY 2018
Province, City or Municipality: North Cotabato, Matalam
| Program or Project | Location | Total | Date Started | Target | Project Status |  | No. of
|  |  | Cost |  | Completion | % of | Total Cost | Extensions, | Remarks
[5 empty] | Date | Completion | Incurred to Date | if any
A | SOCIAL DEVELOPMENT
1 | Construction of Potable Water System with Eleveted Reservoir at Sitio Condring, Marbel |  | 300000
2 | Aid to Construction of Health Center @ Bgy. Lower Malamote |  | 200000
3 | Improvement of Health Center @ Bgy. Manupal |  | 50000
4 | Construction of Multi Purpose Covered @ Bgy. Kilada |  | 2400000 |  |  | 14.97% | 359231.91
5 | Construction of Multi Purpose Covered @ Bgy. Natutungan |  | 2400000
6 | Construction of Potable Water System @ Sitio Angcong, Bgy. BangBang |  | 400000
7 | Aid to Construction of Health Center @ Bgy. Kibudoc |  | 200000 |  |  | 75% | 152300
8 | Aid to Construction of Health Center @ Bgy. Central Malamote |  | 200000
9 | Aid to Construction of Day Care Center @ Sitio Buguac, Kibia |  | 70000 |  |  | 100% | 69000
10 | Costruction of DCC @ Purok Muslim, Bgy. Marbel Proper |  | 70000 |  |  | 90% | 55232
11 | Aid to Construction of Day Care Center @ Sitio Tiocao, Bgy. Linao |  | 70000
12 | Aid to Impvt. Of DCC @ Sitio Layangan, Bgy. Sarayan |  | 100000
13 | Aid to Construction of DCC @ Purok 7, Bgy. Manupal |  | 70000
14 | Aid to Const. of DCC @Sitio New Leon Bgy. Latagan |  | 70000
15 | Aid to Const. of DCC @ Bgy. Taculen Proper |  | 30000
16 | Aid to Impv't. of DCC @ Sitio Masigla and Centro Bgy. Sta. Maria |  | 50000
17 | Aid to Const. of DCC @ Bgy. Central Malamote |  | 70000
18 | Aid to Const. of DCC @ Bgy. Bangbang |  | 70000
19 | Aid to Const. of DCC @ Bgy. Lampayan |  | 70000
20 | Improvement of Health Center @ Bgy.Kabulacan |  | 50000
21 | Improvement of Day Care Center @ Bgy. Kabulacan |  | 50000
22 | Aid to the Costruction of Health Center @ Bgy. New Pandan |  | 70000
23 | Improvement of Day Care Center @ Bgy. Minamaing |  | 70000
24 | Aid to Impv't of Lower Malamote Day Care Center |  | 100000
25 | Aid to the Cons't. of Day Care Center @ Sitio F. Valdevieso, New Bugasong |  | 70000
26 | Aid to the Cons't. of Day Care Center @ Sitio Napasaan, Bgy. Kibia |  | 250000
27 | Aid to the Cons't. of Day Care Center @ Sitio Almarines, Bgy. Taguranao |  | 70000
28 | Aid to the Cons't. of Day Care Center @ Sitio Langka, Bgy. Taguranao |  | 70000
29 | Aid to the Cons't. of Day Care Center @ Sitio Proper, Bgy. Taguranao |  | 250000
30 | Aid to the Construction/Improvement of Birthing Center @ Bgy. Tamped |  | 100000
B | ECONOMIC DEVELOPMENT (Infra-support)
1 | Counterpart Funds for Local, National and Foreign Funded Projects |  | 5000000
2 | Concreting of Municipal/Barangay Main Access Roads |  | 20000000 |  |  | 35% | 5919990
3 | Road Rehabilation (Dimomoyog-Kibia) @ Bgy. Salvacion |  | 150000
4 | Road Rehabilation (Bato-Layangan) @ Bgy. Bato |  | 200000 |  |  | 100% | 190990.8
5 | Road Rehab. (Kabangalasan-Imelda) @ Bgy. Tamped |  | 300000
6 | Road Rehab. (Imelda-Tamped) @ Bgy. Tamped |  | 300000 |  |  | 100% | 293856
7 | Road Rehab. (Sta. Maria-Calura FMR) @ Bgy. Sta. Maria |  | 100000
8 | Aid to Construction of Solar Drier @ Bgy. New Bugasong |  | 100000
9 | Road Rehabilatation (New Alimodian-Sitio Imelda Road) |  | 100000 |  |  | 100% | 95000
10 | Road Rehabilatation (C. Malamote to Taculen) @ Bgy. Taculen |  | 100000 |  |  | 100% | 96450
11 | Road Rehabilatation (Layangan-Pinamaton) @ Bgy. Sarayan |  | 100000 |  |  | 100% | 95472
12 | Road Rehabilatation (Sarayan-Malatab) @ Bgy. Sarayan |  | 100000 |  |  | 100% | 95472
13 | Road Rehabilatation (Napasaan-Buguac) @ Bgy. Kibia |  | 100000
14 | Road Rehabilatation (S. Patnungon-Maligaya) @ Bgy. New Pandan |  | 100000 |  |  | 100% | 95472
15 | Road Rehab. (Bangbang via Kinilid) |  | 100000
16 | Road Rehabilatation (Latagan-Sitio New Leon Road) and (Latagan-Sitio San |  | 100000 |  |  | 100% | 95472
17 | Construction of Solar Drier @ Purok 1, Bgy. New Abra |  | 100000
18 | Road Rehabilatation (New Abra-Israel) @ Bgy. New Abra |  | 100000
19 | Road Rehabilatation (Purok 1-Purok 7) @ Bgy. Lampayan |  | 75000
20 | Road Rehabilatation (Purok 2A-Purok 2B) @ Bgy. Lampayan |  | 75000
21 | Road Rehab. (H-way to Dump Site) @ Bgy. C. Malamote |  | 50000
22 | Road Rehab.Migcuan-Sarayan via Eva and New Alimodian |  | 200000
23 | Road Rehab. (New Tigbawan to Kabulacan) @ Bgy. Kabulacan |  | 100000
24 | Road Rehab @ Sitio Dimahook, Bgy. Tamped |  | 100000
25 | Road Rehab @ Sitio Maligaya, Bgy. Tamped |  | 100000
26 | Road Rehab of ESMAR Road @ Bgy. Estado |  | 100000
27 | Construction of 2 units Solar Drier @ Bgy. Taguranao |  | 200000
C | ENVIRONMENTAL MANAGEMENT(9000)
1 | Aid to SLF Operation & Procurement of Social Waste Collection Equipment |  | 7111711.2
2 | Reforestation: Procurement of Tree Planting Materials (Forest Trees & High Value Crops) |  | 500000
| Total |  | 43801711.2 |  |  |  | 7613938.71
We hereby certify that we have reciewed the contents and hereby attest to
the veracity and correctness of the data or information contained in this
document.
| LERIO D. MIGUEL, CPA | [5 empty] | CHERYL V. CATAMCO, RN
| Municipal Accountant | [5 empty] | Municipal Mayor