## 20%-2020
FDP Form 7-20% Component of the IRA Utilization
UTILIZATION OF THE 20% COMPONENT OF IRA FOR DEVELOPMENT PROJECTS
2nd Quarter, CY 2020
Province, City or Municipality: North Cotabato, Matalam
| Program or Project | Location | Total | Date Started | Target | Project Status |  | No. of
|  |  | Cost |  | Completion | % of | Total Cost | Extensions, | Remarks
[5 empty] | Date | Completion | Incurred to Date | if any
A | SOCIAL DEVELOPMENT
1 | Construction of Day Care Cneter at Brgy. Poblacion |  | 200000
2 | Construction of PWS with concrete resevior at Purok 2, Estado |  | 300000
3 | Construction of Grouted Drainage Canal approx. 100ml @ Salvacion |  | 200000
4 | Extension of Water Line from Purok Mangga-Lokiki, Bangbang |  | 300000
5 | Rehab of Water Pipelines (2000lm)@ Purok Malipayonm Minamaing |  | 400000
6 | Const. of additional 1span MP Covered Court @ Kidama |  | 300000
7 | Const. of watr system with 10kV Transformer, Submersible Pump & Concrete reservior at Purok 7, Tamped Proper |  | 600000
8 | Aid to the Renovation of Health Center at New Bugasong |  | 100000
9 | Improvement of Multi-Purpose Covered Court at Sta. maria |  | 500000 |  |  | 80% | 346335
10 | Expanbsion of PWS from Purok Mhigugmaon to Kaunlaran, Latagan |  | 300000
11 | Cons. Of PWS w/ Concrete Reservior @ Purok Tanglaw, Sta. Maria |  | 300000
12 | Rehabilitation of water pipeline at Bato |  | 300000
B | ECONOMIC DEVELOPMENT (Infra-support)
1 | Const. of Solar Drier @ Sitio Maligaya, L. Malamote |  | 250000 |  |  | 50% | 120960
2 | Road Rehab from Sitio Layangan to Pondoc, Sarayan |  | 200000
3 | Road Rahab from Purok Centro ro Dam Site (irrigatioN) @ C. Malamote |  | 75000 |  |  | 100% | 73580
4 | Opening of Road from Sitio Kulog to Valdevieso (Arakan Waterfalls), Arakan |  | 300000
5 | Construction of Solar Drier at Sitio Kulog, Arakan |  | 300000 |  |  | 50% | 135769
6 | Rehab of Sitio Kulog to Arakan Road, Arakan |  | 300000 |  |  | 23.31% | 69944
7 | Concreting of C. Malamote-SLF Site Road |  | 5000000 |  |  | 94.81% | 4740651.15
8 | Concreting of Road from Purol Maligaya to Daisy, Marbel (200 m) |  | 1500000
9 | Rehab of Sto. Cano, Linao Road |  | 200000
10 | Concreting of 70 meters road at Lampayan Proper (3meters lane) |  | 350000
11 | Concreting of Dalapitan - New Pandan Road (200ml) |  | 2000000
12 | Rehabilitation/Opening of West Patadon Road |  | 300000
13 | Rehab of road from Purok Proper - Biao leading to hanging bridge, Ilian |  | 100000
14 | Construction of Solar Drier at Ilian |  | 250000 |  |  | 50% | 120960
15 | Rehab of Road from Purok 4B, Kabulacan - Sitio Rehab, Natutungan |  | 100000
16 | Rehab of Road at Purok 5,6 & 7 (Purok 5-Rehab Site), Manupal |  | 100000 |  |  | 100% | 98072
17 | Cons. Of Solar Drier at Purok 6 (Leonard) at Manubuan |  | 250000 |  |  | 50% | 120960
18 | Rehab of Road from Purok Langka - Purok 6, Pinamaton |  | 200000
19 | Opening of Road at Purok Pag-asa 2 to Purok Malipayon, Minamaing |  | 300000
20 | Concreting of 300 meters road Poblacion (rados) to Kidama |  | 3000000
21 | Rehab of Taculen- P. Liwa2x Road |  | 150000
22 | Concreting of 150 meters Road from Purok 8 to 6, Kilada |  | 2000000
23 | Rehab of Road from Sitio Buguac to Napasaan, Kibia |  | 100000
24 | Rehab of Road from Purok 2 to 11, Kibia |  | 100000
25 | Road Concreting of 350 meters, along kibia-buguac road, kibia |  | 3500000
26 | Opening of Road from Purok 2, Kibia to Sitio Dimomoyog , Salvacion |  | 150000
27 | Concreting of Taculen-C.Malamote Road, Taculen (200m) |  | 2000000
28 | Construction of Solar Drier & Multi-Purpose Waehouse (MARPICO), Linao |  | 300000
29 | Construction of Solar Drier at Purok 1 (Kurbada), New Bugasong |  | 250000 |  |  | 50% | 120960
30 | Const. of Solar Drier at Sitio Maligaya, L. Malamote ( L.Malamote Womes Ass.) |  | 250000 |  |  | 50% | 120960
31 | Const. of Solar Drier at Purok, Pioneer, Kibudoc (Kibudoc Coconut FA) |  | 250000 |  |  | 50% | 120960
32 | Opening of Road from Sitio to New Abra Proper |  | 200000
33 | Const. of Solar drier at Purok 5, Kilada ( Chrislam FA) |  | 250000
34 | Const. of Solar Drier at Purok 13, (Niyugan), Kibia (Kibia FA) |  | 250000 |  |  | 50% | 120960
35 | Rehab of Brgy. Road National Highway-Centro Sta. Maria-Purok Namnama-Purok Bagong Silang-Purok Sto.nino-Kabalangasan Road, Sta. Maria 3.7kms |  | 300000
36 | Rehabilitation of Central Malamote-F. Valdevieso Road (going to SLF Site) |  | 150000 |  |  | 72.67% | 109000
37 | Concreting of Bonifacio St., Poblacion (200m) |  | 2000000
38 | Loan Repayment (DBP) |  | 22000000 |  |  | 35.93% | 7904310.35
C | ENVIRONMENTAL MANAGEMENT(9000)
1 | Aid to SLF Operation |  | 1000000 |  |  | 3.38% | 33800
2 | Support to reforestation program, projects & activities |  | 249389.2
| Total |  | 54324389.2 |  |  |  | 14358181.5
We hereby certify that we have reciewed the contents and hereby attest to
the veracity and correctness of the data or information contained in this
document.
| SAMUEL F. FAELDONIA | [5 empty] | OSCAR M. VALDEVIESO
| Municipal Budget Officer | [5 empty] | Municipal Mayor