## 20%-2019
FDP Form 7-20% Component of the IRA Utilization
UTILIZATION OF THE 20% COMPONENT OF IRA FOR DEVELOPMENT PROJECTS
4th Quarter, CY 2019
Province, City or Municipality: North Cotabato, Matalam
| Program or Project | Location | Total | Date Started | Target | Project Status |  | No. of
|  |  | Cost |  | Completion | % of | Total Cost | Extensions, | Remarks
[5 empty] | Date | Completion | Incurred to Date | if any
A | SOCIAL DEVELOPMENT
1 | Construction of Day Care Cneter at Purok 5 & 6, Kidama |  | 200000 |  |  |  | 143591
2 | Construction of PWS Elevated Reservior at Purok 1, Manupal |  | 300000 |  |  |  | 199169
3 | Construction of PWS at Brgy. Kilada |  | 300000
4 | Construction of Day Care Center at Sitio Marva, Taguranao |  | 200000 |  |  |  | 143591
5 | Construction of Day Care Center at Sitio Centro, Taguranao |  | 200000 |  |  |  | 143591
6 | Construction od PWS at Sitio Condring, Marbel |  | 300000
7 | Construction of Day Care Center at Purok 2, New Bugasong |  | 200000 |  |  |  | 143591
8 | Construction of Day Care Center at Sitio Igsoro, New Bugasong |  | 200000 |  |  |  | 143591
9 | Provision of Submersible Pump at Purok 8, New Bugasong |  | 150000 |  |  | 100% | 149808
10 | Construction of PWS Elevated Reservior at Purok Centro, Kibia |  | 300000
11 | Aid to Construction of Day Care Center at Sitio Layangan, Sarayan |  | 200000 |  |  |  | 143591
12 | Provision of PWS Reservior at Brgy, Pinamaton |  | 300000
B | ECONOMIC DEVELOPMENT (Infra-support)
1 | Road Rehabilitation of C. Malamote-Purok Liwa2x (5kms) |  | 150000
2 | Road Rehabilitation of Budzi-Natutungan (Ilian Side, 3 kms) |  | 100000
3 | Construction of Solar Drier at Sitio Takidegen, Ilian |  | 300000 |  |  | 100% | 299220
4 | Rehabilitation of Road at Lower Malamote |  | 150000 |  |  | 100% | 145858.2
5 | Road Rehabilitation of Sitio Calura-New Bacolod, Minamaing (3kms) |  | 150000 |  |  | 100% | 144199.25
6 | Opening of Road of Purok Pag-asa 2 to Purok Malipayon (500 mtrs) |  | 100000
7 | Road Rehabilitation of New Abra to New Israel |  | 150000
8 | Opening of Road at Tigbawan-Purok 5, New Abra (500 mtrs.) |  | 100000 |  |  | 100% | 99958
9 | Road Rehabilitation of Purok Marang-Boundary Pinamaton Road (New Alimodian Side, 3 kms) |  | 200000
10 | Road Rehabilitation of Sto. Nino-Bagong Silang Road (10 kms) |  | 300000 |  |  | 100% | 284330
11 | Road Rehabilitation of Sitio Langka-Almarines Road, Taguranao |  | 200000
12 | Road Rehabilitation of Brgy. Marbel |  | 100000
13 | Road Rehabilitation of Brgy. Lampayan |  | 100000 |  |  | 100% | 99015
14 | Opening of Road at Sitio Tigbawan-New Maaw-Bugtong Bukid, Kabulacan |  | 200000 |  |  | 100% | 196196
15 | Road Rehabilitation of Pinamaton-Lamanan Road, Pinamaton Road (7kms) |  | 250000 |  |  | 100% | 241889.15
16 | Road Rehabilitation of Purok Namnama, Taculen-Boundary Dalapitan Road (5kms) |  | 200000
17 | Construction of Solar Drier at Taculen |  | 300000 |  |  |  | 207220
18 | Rehabilitation of Solar Drier at Kibudoc |  | 300000 |  |  |  | 200868
19 | Road Rehabilitation of Sitio Kulog-Pulangi, Arakan (3kms) |  | 250000 |  |  | 100% | 248769
20 | Road Rehabilitation of Sitio Kulog-Itud, Arakan (5kms) |  | 300000 |  |  | 100% | 298512.25
21 | Road Rehabilitation of Layangan-Bato Road |  | 300000
22 | Road Rehabilitation of Purok Santan-Sitio Angcong Road, Bangbang |  | 200000 |  |  | 100% | 194083.12
23 | Road Rehabilitation of Brgy. Manubuan |  | 150000 |  |  | 100% | 145745
24 | Road Rehabilitation of Purok 1-6 Road, W. Patadon |  | 200000 |  |  | 100% | 199969
25 | Opening of Road at Brgy. Estado |  | 200000
26 | Construction of Overflow Bridge at Purok 2, Estado |  | 200000
27 | Road Rehabilitation at Marbel-Estado Road (Estado Side) |  | 200000 |  |  | 100% | 196196
28 | Expansion of Esmar SD |  | 300000 |  |  |  | 209220
29 | Road Rehabilitation at Purok 5-8, Brgy. Salvacion (500 mtrs) |  | 200000 |  |  | 100% | 196560
30 | Road Rehabilitation at Purok 7, Sitio Dimomoyog-Boundary Kibia Road (Salvacion Side, 3 kms) |  | 250000 |  |  | 100% | 245784
31 | Road Rehabilitation at Marva-Langka Road, Taguranao (3kms) |  | 200000
32 | Road Rehabilitation at Langka-Imelda, Taguranao (5kms) |  | 300000 |  |  | 100% | 297150
33 | Road Rehabilitation at Taguranao-Almarines Road, Taguranao (3kms) |  | 200000 |  |  | 100% | 198082.5
34 | Road Rehabilitation at Taguranao-Bato Road, Taguranao (3kms) |  | 200000 |  |  | 100% | 196196
35 | Road Rehabilitation at Sitio Centro-Maligaya Road, Tamped (7kms) |  | 300000 |  |  |  | 141217
36 | Road Rehabilitation at Purok 6-Manobo Village Road, Tamped (2 kms) |  | 150000 |  |  | 100% | 141217
37 | Road Rehabilitation at Purok Narra-Langka Road, Dalapitan (700 mtrs) |  | 100000 |  |  | 100% | 82719
38 | Road Rehabilitation at Purok 13-9 Road, Kibia ( 2 kms) |  | 150000
39 | Road Rehabilitation at Purok 1-14 Road, Kibia (2 kms) |  | 150000
40 | Road Rehabilitation at Sitio Natipakan-Mabuhay Road, Latagan (6kms) |  | 300000 |  |  | 100% | 292620
41 | Road Rehabilitation at Sitio Patnungon-Maligaya Road, New Pandan (4 kms) |  | 200000 |  |  | 100% | 199969
42 | Road Rehabilitation at Purok 4-Maligaya Road, New Pandan (4 kms) |  | 250000
43 | Road Rehabilitation at Sarayan proper-Sitio Maiwag Road, Sarayan ( 8kms) |  | 300000 |  |  | 100% | 294268
44 | Road Rehabilitation at Sitio Lamanan-Purok 8 Road, Sarayan |  | 300000
45 | Taculen-Dalapitan Road Opening |  | 200000
46 | Road Rehabilitation of Linao-Latagan Road |  | 469549.6
47 | Concreting of Sta. Maria-Linao-Latagan Road (900 mtrs) |  | 9000000 |  |  | 100% | 8994780.08
48 | Loan Repayment (Debt Servicing) |  | 24000000 |  |  |  | 3423102.95
C | ENVIRONMENTAL MANAGEMENT(9000)
1 | Aid to SLF Operation & Solid Waste Collection of the Municipality |  | 2000000 |  |  |  | 836759.3
2 | Tree Growing Activities and Procurement of Planting Materials |  | 500000
| Total |  | 48219549.6 |  |  |  | 20162195.8
We hereby certify that we have reciewed the contents and hereby attest to
the veracity and correctness of the data or information contained in this
document.
| SAMUEL F. FAELDONIA | [5 empty] | OSCAR M. VALDEVIESO
| Municipal Budget Officer | [5 empty] | Municipal Mayor