## 20%-2022
FDP Form 7-20% Component of the IRA Utilization
UTILIZATION OF THE 20% COMPONENT OF IRA FOR DEVELOPMENT PROJECTS
1st Quarter, CY 2022
Province, City or Municipality: North Cotabato, Matalam
| Program or Project | Location | Total | Date Started | Target | Project Status |  | No. of
|  |  | Cost |  | Completion | % of | Total Cost | Extensions, | Remarks
[5 empty] | Date | Completion | Incurred to Date | if any
A | SOCIAL DEVELOPMENT
1 | Installation of Water System at Sitio Pangipasan | Brgy. Lampayan | 300000
2 | Construction of Water System at Purok 1 | Brgy. New Abra | 300000 |  |  |  | 199563
3 | Expansion of Latagan Potable Water System | Brgy. Latagan | 200000
4 | Expansion of Napasaan Potable Water System | Brgy. Kibia | 300000
5 | Construction of 8ft. X 8ft. Reservoir for Potable Water System | Brgy. Linao | 300000 |  |  |  | 263218
6 | Construction of Reservoir for Potable Water System | Brgy. Manupal | 300000
7 | Aid to Improvement of Child Development Center | Brgy. New Abra | 100000
8 | Aid to Construction of Purok Centro Barangay Health Station | Brgy. Taguranao | 200000
9 | Aid to Renovation of Child Development Center | Brgy. West Patadon | 100000
10 | Aid to Improvement of Multi-Purpose Building | Brgy. Minamaing | 150000
11 | Construction of Potable Water System | Brgy. Kabulacan | 300000
| Sub-total (Social) |  | 2550000 |  |  |  | 462781
PPAs for COVID-19 Vaccination (Summary)
12 | Procurement of COVID-19 Vaccination Supplies |  | 1164600
13 | Procurement of COVID-19 Vaccines |  | 10000000
14 | Monitoring of Vaccines for AEFI |  | 479025
15 | Provision of Meals of Health Personnel and Vaccinnee during Vaccination |  | 2500000
16 | Internet Subscription Expenses |  | 18000
17 | Provision of Fuel for the Transport of Vaccines and Vaccinee |  | 500000
18 | Provision of Storage for COVID-19 Vaccines |  | 100000
19 | Conduct of Information and Education Campaign on COVID-19 Vaccines |  | 181250
20 | Proper Disposal of Infectious Wastes |  | 509800
21 | Miscellaneous Expenses (Payment for Light and Water Bill of the Vaccination Venue) |  | 24000
21 | Provision of Honorarium for Medical Doctor Attending to COVID-19 Vaccinees |  | 500000
23 | Procurement of PPEs for COVID-19 Frontliners |  | 1500000
24 | Procurement of Rapid Testing Kits and Disinfectants for COVID-19 Respons |  | 1000000
25 | Provision of Food and Medicine Assistance to Quarantined Families due to COVID-19 |  | 5000000
| Sub-total (COVID-19 Vaccination Summary) |  | 23476675 |  |  |  | 0
B | ECONOMIC DEVELOPMENT (Infra-support)
26 | Construction of F. Valdevieso Solar Dryer | Brgy. New Bugasong | 300000 |  |  |  | 138821
27 | Construction of D. Almarines Solar Dryer | Brgy. Taguranao | 350000
28 | Construction of Kidama Solar Dryer | Brgy. Kidama | 300000
29 | Construction of Purok 2 Solar Dryer | Brgy. Manupal | 300000
30 | Construction of Purok 1 Solar Dryer | Brgy. West Patadon | 300000
31 | Construction of Purok 4 Solar Dryer | Brgy. West Patadon | 300000
32 | Additional 370Ln.m. Concreting of Kibia-Latagan Road | Kibia-Latagan Road | 4100000 |  |  |  | 613487.55
33 | Additional 200Ln.m. Concreting of Linao-Bangbang via Kinilid Road | Brgy. Linao | 2700000 |  |  |  | 404166.71
34 | Concreting of 200 Ln.m. Central Malamote-SLF Road | Brgy. Central Malamote | 2200000 |  |  |  | 328807.9
35 | Concreting of 200 Ln.m. Dalapitan-New Pandan via Purok Bayabas Road | Brgy. New Pandan | 2200000 |  |  |  | 328948.26
36 | Concreting of 200 Ln.m. Central Malamote-Taculen Road | Brgy. Taculen | 2200000 |  |  |  | 328928.28
37 | Additional Concreting of 250 Ln.m. Highway-Junction Pinamaton Road | Brgy. Pinamaton | 2800000 |  |  |  | 419211.47
38 | Concreting of 300 Ln.m. Taguranao-Arakan Road | Brgy. Taguranao | 5500000 |  |  |  | 823832.85
39 | Concreting of 200 Ln.m. Lower Malamote-New Pandan Road | Brgy. Lower Malamote | 2250000 |  |  |  | 336312.62
40 | Loan Repayment to DBP |  | 25000000 |  |  |  | 4187072.18
| Sub-total (Economic) |  | 50800000 |  |  |  | 7909588.82
C | ENVIRONMENTAL MANAGEMENT(9000)
41 | Aid to SLF Operation and Grabage Collections |  | 1000000 |  |  |  | 195160
42 | Support to Reforestation Program (National Greening and Earth Day) |  | 261629.6
| Sub-total (Environmental) |  | 1261629.6 |  |  |  | 195160
| Total |  | 78088304.6 |  |  |  | 8567529.82
We hereby certify that we have reviewed the contents and hereby attest to
the veracity and correctness of the data or information contained in this
document.
| SAMUEL F. FAELDONIA | [5 empty] | OSCAR M. VALDEVIESO
| Municipal Budget Officer | [5 empty] | Municipal Mayor