## tf-2019
FDP Form 6-Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
4th Quarter, CY 2019
Province, City or Municipality: North Cotabato, Matalam
| Programs or Projects | Location | Total | Date Started | Target | Project Status |  | No. of
|  |  | Cost |  | Completion | % of | Total Cost | Extensions, | Remarks
[5 empty] | Date | Completion | Incurred to Date | if any
1 | Multi-purpose Building and Support to Agr'l. Production | West Patadon | 2500000 |  | 01/25/19 | 100% | 2497648.1
2 | Provision of Livelihood on Cattle Production | Ilian | 300000 |  | 03/08/19 | 100% | 240000
3 | Provision of Livelihood on Cattle Production | Arakan | 300000 |  | 03/08/19 | 100% | 240000
4 | Provision of Livelihood on Cattle Production | Bangbang | 300000 |  | 03/08/19 | 100% | 240000
5 | Provision of Livelihood on Cattle Production | Pinamaton | 300000 |  | 03/04/19 |  | 240000
6 | Provision of Corn Sheller | Natutungan | 300000 |  | 07/31/19 | 100% | 300000
7 | Acquisition of Post-Harvest Facilities | Poblacion | 300000 |  | 07/31/19 | 100% | 300000
8 | Provision of Travelling Rice Mill | Kilada | 300000 |  | 07/31/19 | 100% | 300000
9 | Post Harvest Facilities (Drier) BUB Program | Sitio Dimomoyog & New Bugasong | 200000 |  |  | 100% | 200000
10 | Construction of 1 Unit Solar Dryer | Kabulacan | 300000 |  | 06/03/19 | 100% | 240000
11 | Construction of 1 Unit Solar Dryer | Latagan | 300000 |  | 06/03/19 | 100% | 240000
12 | Construction of 1 Unit Solar Dryer | Taguranao | 300000 |  | 06/20/19 | 100% | 240000
13 | Construction of Tribal Hall | Linao | 300000 |  | 06/03/19 | 100% | 240000
14 | Expansion of PWS | Minamaing | 300000 |  | 08/07/19 | 100% | 240000
15 | Expansion of PWS | Sarayan | 300000 |  | 06/03/19 | 100% | 240000
16 | Construction of MPB | West Patadon | 300000 |  | 07/29/19 | 100% | 240000
17 | Expansion of PWS | Tamped | 300000 |  | 07/29/19 | 100% | 240000
18 | Construction of 1 Unit Solar Dryer | Kibudoc | 300000 |  | 06/20/19 | 100% | 240000
19 | Construction of 1 Unit Solar Dryer | Lampayan | 300000 |  | 06/03/19 | 100% | 240000
20 | Construction of Tribal Hall | L. Malamote | 300000 |  | 06/03/19 | 100% | 240000
21 | Construction of 1 Unit Solar Dryer | Manubuan | 300000 |  | 06/20/19 | 100% | 240000
22 | Construction of MPB | New Pandan | 300000 |  | 09/25/19 | 100% | 300000
23 | Establishment of MRF | Poblacion | 297216.38 |  | 04/17/19 | 100% | 297216.38
24 | Provision of Corn Sheller | New Abra | 300000 |  | 06/20/19 | 100% | 240000
25 | Concreting of New Alimodian-Imelda Road | Imelda | 7410936 |  | 12/27/19 | 100% | 7335387.99
26 | Potable Water System @ Lampayan | Lampayan | 2000000 |  | 11/05/19 | 100% | 2000000
27 | Potable Water System @ West Patadon | West Patadon | 2000000 |  | 11/05/19 | 100% | 2000000
28 | Potable Water System @ Bangbang | Bangbang | 2000000 |  | 11/05/19 | 100% | 2000000
29 | Concreting of New Alimodian-Imelda Road | Imelda | 6242000 |  | 12/27/19 | 100% | 6242000
| Total |  | 28950152.38 |  |  |  | 27852252.47
We hereby certify that we have reciewed the contents and hereby attest to
the veracity and correctness of the data or information contained in this
document.
| SAMUEL F. FAELDONIA |  | LERIO D. MIGUEL, CPA |  |  |  | OSCAR M. VALDEVIESO
| Municipal Budget Officer |  | Municipal Accountant |  |  |  | Municipal Mayor

## 20%-2019
FDP Form 7-20% Component of the IRA Utilization
UTILIZATION OF THE 20% COMPONENT OF IRA FOR DEVELOPMENT PROJECTS
4th Quarter, CY 2019
Province, City or Municipality: North Cotabato, Matalam
| Program or Project | Location | Total | Date Started | Target | Project Status |  | No. of
|  |  | Cost |  | Completion | % of | Total Cost | Extensions, | Remarks
[5 empty] | Date | Completion | Incurred to Date | if any
A | SOCIAL DEVELOPMENT
1 | Construction of Day Care Cneter at Purok 5 & 6, Kidama |  | 200000 |  |  |  | 143591
2 | Construction of PWS Elevated Reservior at Purok 1, Manupal |  | 300000 |  |  |  | 199169
3 | Construction of PWS at Brgy. Kilada |  | 300000
4 | Construction of Day Care Center at Sitio Marva, Taguranao |  | 200000 |  |  |  | 143591
5 | Construction of Day Care Center at Sitio Centro, Taguranao |  | 200000 |  |  |  | 143591
6 | Construction od PWS at Sitio Condring, Marbel |  | 300000
7 | Construction of Day Care Center at Purok 2, New Bugasong |  | 200000 |  |  |  | 143591
8 | Construction of Day Care Center at Sitio Igsoro, New Bugasong |  | 200000 |  |  |  | 143591
9 | Provision of Submersible Pump at Purok 8, New Bugasong |  | 150000 |  |  | 100% | 149808
10 | Construction of PWS Elevated Reservior at Purok Centro, Kibia |  | 300000
11 | Aid to Construction of Day Care Center at Sitio Layangan, Sarayan |  | 200000 |  |  |  | 143591
12 | Provision of PWS Reservior at Brgy, Pinamaton |  | 300000
B | ECONOMIC DEVELOPMENT (Infra-support)
1 | Road Rehabilitation of C. Malamote-Purok Liwa2x (5kms) |  | 150000
2 | Road Rehabilitation of Budzi-Natutungan (Ilian Side, 3 kms) |  | 100000
3 | Construction of Solar Drier at Sitio Takidegen, Ilian |  | 300000 |  |  | 100% | 299220
4 | Rehabilitation of Road at Lower Malamote |  | 150000 |  |  | 100% | 145858.2
5 | Road Rehabilitation of Sitio Calura-New Bacolod, Minamaing (3kms) |  | 150000 |  |  | 100% | 144199.25
6 | Opening of Road of Purok Pag-asa 2 to Purok Malipayon (500 mtrs) |  | 100000
7 | Road Rehabilitation of New Abra to New Israel |  | 150000
8 | Opening of Road at Tigbawan-Purok 5, New Abra (500 mtrs.) |  | 100000 |  |  | 100% | 99958
9 | Road Rehabilitation of Purok Marang-Boundary Pinamaton Road (New Alimodian Side, 3 kms) |  | 200000
10 | Road Rehabilitation of Sto. Nino-Bagong Silang Road (10 kms) |  | 300000 |  |  | 100% | 284330
11 | Road Rehabilitation of Sitio Langka-Almarines Road, Taguranao |  | 200000
12 | Road Rehabilitation of Brgy. Marbel |  | 100000
13 | Road Rehabilitation of Brgy. Lampayan |  | 100000 |  |  | 100% | 99015
14 | Opening of Road at Sitio Tigbawan-New Maaw-Bugtong Bukid, Kabulacan |  | 200000 |  |  | 100% | 196196
15 | Road Rehabilitation of Pinamaton-Lamanan Road, Pinamaton Road (7kms) |  | 250000 |  |  | 100% | 241889.15
16 | Road Rehabilitation of Purok Namnama, Taculen-Boundary Dalapitan Road (5kms) |  | 200000
17 | Construction of Solar Drier at Taculen |  | 300000 |  |  |  | 207220
18 | Rehabilitation of Solar Drier at Kibudoc |  | 300000 |  |  |  | 200868
19 | Road Rehabilitation of Sitio Kulog-Pulangi, Arakan (3kms) |  | 250000 |  |  | 100% | 248769
20 | Road Rehabilitation of Sitio Kulog-Itud, Arakan (5kms) |  | 300000 |  |  | 100% | 298512.25
21 | Road Rehabilitation of Layangan-Bato Road |  | 300000
22 | Road Rehabilitation of Purok Santan-Sitio Angcong Road, Bangbang |  | 200000 |  |  | 100% | 194083.12
23 | Road Rehabilitation of Brgy. Manubuan |  | 150000 |  |  | 100% | 145745
24 | Road Rehabilitation of Purok 1-6 Road, W. Patadon |  | 200000 |  |  | 100% | 199969
25 | Opening of Road at Brgy. Estado |  | 200000
26 | Construction of Overflow Bridge at Purok 2, Estado |  | 200000
27 | Road Rehabilitation at Marbel-Estado Road (Estado Side) |  | 200000 |  |  | 100% | 196196
28 | Expansion of Esmar SD |  | 300000 |  |  |  | 209220
29 | Road Rehabilitation at Purok 5-8, Brgy. Salvacion (500 mtrs) |  | 200000 |  |  | 100% | 196560
30 | Road Rehabilitation at Purok 7, Sitio Dimomoyog-Boundary Kibia Road (Salvacion Side, 3 kms) |  | 250000 |  |  | 100% | 245784
31 | Road Rehabilitation at Marva-Langka Road, Taguranao (3kms) |  | 200000
32 | Road Rehabilitation at Langka-Imelda, Taguranao (5kms) |  | 300000 |  |  | 100% | 297150
33 | Road Rehabilitation at Taguranao-Almarines Road, Taguranao (3kms) |  | 200000 |  |  | 100% | 198082.5
34 | Road Rehabilitation at Taguranao-Bato Road, Taguranao (3kms) |  | 200000 |  |  | 100% | 196196
35 | Road Rehabilitation at Sitio Centro-Maligaya Road, Tamped (7kms) |  | 300000 |  |  |  | 141217
36 | Road Rehabilitation at Purok 6-Manobo Village Road, Tamped (2 kms) |  | 150000 |  |  | 100% | 141217
37 | Road Rehabilitation at Purok Narra-Langka Road, Dalapitan (700 mtrs) |  | 100000 |  |  | 100% | 82719
38 | Road Rehabilitation at Purok 13-9 Road, Kibia ( 2 kms) |  | 150000
39 | Road Rehabilitation at Purok 1-14 Road, Kibia (2 kms) |  | 150000
40 | Road Rehabilitation at Sitio Natipakan-Mabuhay Road, Latagan (6kms) |  | 300000 |  |  | 100% | 292620
41 | Road Rehabilitation at Sitio Patnungon-Maligaya Road, New Pandan (4 kms) |  | 200000 |  |  | 100% | 199969
42 | Road Rehabilitation at Purok 4-Maligaya Road, New Pandan (4 kms) |  | 250000
43 | Road Rehabilitation at Sarayan proper-Sitio Maiwag Road, Sarayan ( 8kms) |  | 300000 |  |  | 100% | 294268
44 | Road Rehabilitation at Sitio Lamanan-Purok 8 Road, Sarayan |  | 300000
45 | Taculen-Dalapitan Road Opening |  | 200000
46 | Road Rehabilitation of Linao-Latagan Road |  | 469549.6
47 | Concreting of Sta. Maria-Linao-Latagan Road (900 mtrs) |  | 9000000 |  |  | 100% | 8994780.08
48 | Loan Repayment (Debt Servicing) |  | 24000000 |  |  |  | 3423102.95
C | ENVIRONMENTAL MANAGEMENT(9000)
1 | Aid to SLF Operation & Solid Waste Collection of the Municipality |  | 2000000 |  |  |  | 836759.3
2 | Tree Growing Activities and Procurement of Planting Materials |  | 500000
| Total |  | 48219549.6 |  |  |  | 20162195.8
We hereby certify that we have reciewed the contents and hereby attest to
the veracity and correctness of the data or information contained in this
document.
LERIO D. MIGUEL, CPA
Municipal Accountant

## CF-2019
FDP Form 9-Statement of Cash Flows
(BLGF Memorandum Circular No. 09-2012 dated February 21, 2012, Annex 2)
STATEMENT OF CASH FLOWS
4th, Quarter, CY 2019
Province, City or Municipality: North Cotabato, Matalam
Cash Flows from Operating Activities:
Cash Inflows:
| Collections from Taxpayers | 21157559.57
| Share from Internal Revenue Collections | 240898296
| Receipts from Sale of Goods or Services | 8227208.86
| Interest Income | 1016365.05
Dividend Income
| Other Receipts | 49512566.77
| Total Cash Inflow | 320811996.25
Cash Outflows:
Payments -
| To suppliers/creditors | 142149989.84
| To Employees | 73391449.95
| Interest Expenses | 4165662.2
| Other Expenses | 29119800.67
| Total Cash Outflow | 248826902.66
| Net Cash from Operating Activities |  |  | 71985093.59
Cash Flows from Investing Activities:
Cash Inflows:
| From Sale of Property, Plant and Equipment | 0
| From Sale of Debt Securities of Other Entities | 0
| From Coll. of Principal on Loans to Other Entities | 0
| Total Cash Inflows | 0
Cash Outflows:
| To Purchase Property, Plant and Equipment | 182094299.16
| To Purchase Debt Securities of Other Entities | 0
| Total Cash Outflow | 182094299.16
| Net Cash from Investing Activities: |  |  | -182094299.16
Cash Flows from Financing Activities
Cash Inflows:
| From Issuance of Debt Securities | 0
| From Acquisition of Loan | 136441290.56
| Total Cash Outflow | 136441290.56
Cash Outflows:
Retirement/Redemption of Dedt Securities
| Payment of Loan Amortization | 0
| Total Cash Outflow | 136441290.56
| Net Cash from Financing Activities | -45653008.6
Net Increase in Cash |  |  |  | 26332084.99
Cash at Beginning of the Period |  |  |  | 326271011.92
Cash at the End of the Period |  |  |  | 352603096.91
We hereby certify that we have reviewed the contents and hereby attest to the veracity and
correctness of the data or information contained in this documents
| LERIO D. MIGUEL, CPA |  | OSCAR M. VALDEVIESO
| Municipal Accountant |  | Municipal Mayor

## sef-util. -2019
FDP Form 11-SEF Utilization
(DepEd-DBM-DILG Circular No. 1 s. 2017, SEF Budget Accountability Form No. 1)
SPECIAL EDUCTAION FUND UTILIZATION
4th Quarter, CY 2019
Province/City/Municipality : North Cotabato, Matalam
Receipt from SEF |  | Php | 5098831.82
Less: | DISBURSEMENTS (broken down by expense
class and by object of expenditure)
Personal Services
| Salaries & Wages - Casual |  | 0
Maintenance and Other Operating Expenses
| Office Supplies Expenses |  | 0
| Fuel, Oil & Lubricant |  | 6474
| Other Supplies and Materials Expenses |  | 0
| Repair & Maint.-School Building |  | 0
| Representation Expenses |  | 0
| Donations |  | 2610428.64
| Depreciations |  | 324789.97
| Other Operating Expenses |  | 0
| Capital Outlay |  | 0
| Financial Expenses |  | 0
Sub-Total |  |  | 2941692.61
Balance |  | Php | 2157139.21
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data
or information contained in this document
| LERIO D. MIGUEL, CPA | OSCAR M. VALDEVIESO
| Municipal Accountant | LCE, Chairman, LSB

## LDRRM
FDP Form 8- Local Disaster Risk Reduction and Management Fund Utilization
(Commission on Audit Form)
LOCAL DISASTER RISK REDUCTION AND MANAGEMENT FUND UTILIZATION
4th Quarter, CY 2019
Province, City or Municipality: NORTH COTABATO, MATALAM
PARTICULARS |  |  | NDRRMF | From Other LGUs | From Other Sources | Total
| Quick Response Fund | Mitigation Fund
| 30% | 70%
A. Sources of Funds
Current Appropriations | 3613474.2 | 8518868.51 |  | 550000 |  | 12682342.71
Continuing Appropriations | 6345906.08 | 14100143.94 |  |  |  | 20446050.02
Previous Year's Appropriation transferred to the Special Trust Fund
CY 2018 | 2524145.37 | 466716.35 |  |  |  | 2990861.72
CY 2017 | 0 | 0 |  |  |  | 0
CY 2016 | 0 | 0 |  |  |  | 0
CY 2015 | 0 | 0 |  |  |  | 0
Initial Deposit |  | 10000 |  |  |  | 10000
Interest Income |  | 175277.54 |  |  |  | 175277.54
Transfers/Grants | - | - |  |  |  | 0
Total Funds Available | 12483525.65 | 23271006.34 | 0 | 550000 | 0 | 36304531.99
B. Utilization
Medicines | [5 empty] | 0
Food Supplies | 4437592 | 91072 |  |  |  | 4528664
Repair of Evacuation Center |  | 170000 |  |  |  | 170000
Road Networks |  | 319444 |  |  |  | 319444
Supplies and Materials | 3137874.47 |  |  |  |  | 3137874.47
Fuel, Oil and Lubricants |  | 221528 |  |  |  | 221528
Trainings |  | 409690 |  |  |  | 409690
Representation Expenses | 7000 | 11250 |  |  |  | 18250
Flood Control Systems |  | 4041121.28 |  |  |  | 4041121.28
Disaster Response & Recue Equipment |  | 247448.61 |  |  |  | 247448.61
0
0
Total Utilization | 7582466.47 | 5511553.89 | - | 0 | - | 13094020.36
Unutilized Balance | 4901059.18 | 17759452.45 | 0 | 550000 | 0 | 23210511.63
I hereby certify that I have reviewed the contents and hereby attest to the veracity and correctness of data or information contained in this document.
LERIO D. MIGUEL, CPA
Municipal Accountant

## Cash Advance
FDP Form 12 - Unliquidated Cash Advances
ULIQUIDATED CASH ADVANCES
4th QUARTER, 2019
Province, Cty or Municipality: Matalam
Name of Debtor | Amount Balance | Date Granted | Purpose | Amount Due
|  |  |  | Current |  |  | Past Due
|  |  |  | Less than 30 days | 31-90 days | 91-365 days | Over 1 year | Over 2 years | 3 years and above
Jessica B. Parrenas | 15290 | 11/05/19 | Travel |  | 15290
Ralph Ryan Rafael | 25960 | 11/05/19 | Travel |  | 25960
Oscar M. Valdevieso | 432375 | 11/20/19 | CF |  | 432375
Total | 473625 |  |  | 0 | 473625 | 0 | 0 | 0 | 0
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
| LERIO D. MIGUEL, CPA | [5 empty] | OSCAR M. VALDEVIESO
| Municipal Accountant | [5 empty] | Municipal Mayor