## tf-2021
FDP Form 6-Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
4th Quarter, CY 2021
Province, City or Municipality: North Cotabato, Matalam
Programs or Projects | Location | Total | Date Started | Target | Project Status |  | No. of
|  | Cost |  | Completion | % of | Total Cost | Extensions, | Remarks
|  |  |  | Date | Completion | Incurred to Date | if any
NAPASAAN Housing Project | Sitio Kibia, Matalam | 2500000 | 11/11/2021 | 44561 | 100% | 2500000 |  | Fully Implemented
Total |  | 2500000 |  |  |  | 2500000
We hereby certify that we have reciewed the contents and hereby attest to
the veracity and correctness of the data or information contained in this
document.
SAMUEL F. FAELDONIA |  | LERIO D. MIGUEL, CPA |  |  |  | OSCAR M. VALDEVIESO
Municipal Budget Officer |  | Municipal Accountant |  |  |  | Municipal Mayor

## SIPB
FDPP Form 2 - Annual Statement of Indebtedness, Payments and Balances
(DOF-BLGF Memorandum Circular No. 005-2018 dated January 22, 2018, Annex E)
Annual Statement of Indebtedness, Payments and Balances (SIPB)
4th Quarter, 2021
Province, City or Municipality: Matalam
ITEM NO. | PARTICULARS | DETAILS
1 | LGU Income Classification | First Class
2 | Date of Report | 2019-12-31
3 | Lending Institution (Bank or Creditor) | DBP
4 | Certificate Number - NDSC/BC | R12-2018-11-342
5 | Date of Certification - NDSC/BC | 2018-11-13
6 | Monetary Board (MB) Resolution Number | 165
7 | Date of MB Opinion | 01/31/2019
8 | Date of Approval Loan | 10/08/2018
9 | Amount Approved* | 180000000
10 | Maturity Date | 10/08/28 & 03/28/2034
11 | Type of Indebtedness Instrument (Loan, Bond or other form of indebtedness) | Term Loan
12 | Purpose of Indebtedness | Road Concreting/Const. of Public Market
13 | Terms and Conditions: Fixed or Variable | Fixed
14 | Terms and Conditions: No. of Years of Indebtedness | 10 years & 15 years
15 | Terms and Conditions: Interest Rate | 4.62% pa | ,
16 | Terms and Conditions: Grace Period (Number of Months or Years) | 36
17 | Frequency of Payment | Quaterly
18 | Annual Amortization: Principal | 0
19 | Annual Amortization: Interest | 9576794.15
20 | Annual Amortization: Gross Receipt Tax (GRT) | 182013.15
21 | Starting Date of Payment | 03/30/2019
22 | Cumulative Payment from Starting Date: Principal | 24153507.7
23 | Cumulative Payment from Starting Date: Interest | 17010867.94
24 | Cumulative Payment from Starting Date: GRT | 256352.92
25 | Total Amount Released (Availment as of date) | 162472481
26 | Remaining Balance to Date / Undrawn amount (Line 9-25=26) | 17527519
27 | Outstanding Loan Balance After Principal Payment (Line 9-22=27) | 155846492.3
28 | Arrears: Principal (if any) | 0
29 | Arrears: Interest (if any) | 0
30 | Collateral Security | 0
31 | Deposit to bond sinking fund for the year | 0
32 | Sinking fund balance to date, if any | 0
33 | Breakdown of fees and other related costs (of loan) | 1350000
34 | Other relevant terms and conditions (of loan) | 0
Certified correct:
ROSALIA B. BARRACA
Municipal Treasurer

## 20%-2021
FDP Form 7-20% Component of the IRA Utilization
UTILIZATION OF THE 20% COMPONENT OF IRA FOR DEVELOPMENT PROJECTS
4th Quarter, CY 2021
Province, City or Municipality: North Cotabato, Matalam
| Program or Project | Location | Total | Date Started | Target | Project Status |  | No. of
|  |  | Cost |  | Completion | % of | Total Cost | Extensions, | Remarks
[5 empty] | Date | Completion | Incurred to Date | if any
A | SOCIAL DEVELOPMENT
1 | Const. of Multi-purpose Covered Court w/ Facilities at Matalam Evacuation Center (COVID 19 related Project) |  | 3200000 |  |  |  | 1801642.82 |  | Partially
2 | Const. of 1 unit - 2storey Management Office and Quarters w/ facilities (COVID 19 related project @ Evac. Center |  | 4300000 |  |  |  | 1813902.16 |  | Partially
3 | Const. of Guards' Quarter w/ falities @ Evac. Center |  | 500000 |  |  |  | 0 |  | Not Implemented
4 | Aid to Sitio Bubungan Water System @ Linao |  | 150000 |  |  |  | 149885 |  | Fully
5 | Const. of Child Development Center @ Latagan |  | 300000 |  |  |  | 0 |  | Not Implemented
6 | Aid to Bangbang Water System |  | 400000 |  |  |  | 395980 |  | Fully
7 | Const. of Multi-purpose Covered Court one (1) span @ Sitio Marva, Taguranao |  | 400000 |  |  |  | 0 |  | Not Implemented
B | ECONOMIC DEVELOPMENT (Infra-support)
1 | Loan Repayment (DBP) |  | 22000000 |  |  |  | 22000000 |  | Fully
2 | Concreting of SLF Road (C.Malamote-Manubuan) 300 mtrs. |  | 3000000 |  |  |  | 2994851.64 |  | Fully
3 | Rehab of Pinmaton-Bato (via Layangan) Road |  | 500000 |  |  |  | 499040.3 |  | Fully
4 | Rehab of Sarayan-Bato Road |  | 500000 |  |  |  | 498996.3 |  | Fully
5 | Rehab of Bato-Taguranao Road |  | 500000 |  |  |  | 499000.7 |  | Fully
6 | Rehab of Kulog-Sitio Valdevieso Road |  | 500000 |  |  |  | 499032 |  | Fully
7 | Rehab of Kulog-Pulangi Road |  | 500000 |  |  |  | 499005.7 |  | Fully
8 | Const. of 1 unit Solar Drier @ Sitio Mamporang, Arakan |  | 300000 |  |  |  | 241353 |  | Partially
9 | Cpncreting of Latagan-Sitio New Leon Road 150 mtrs. |  | 2250000 |  |  |  | 2244977.03 |  | Fully
10 | Concreting of Purok Kaunlaran-Linao Road 150 mtrs. |  | 2250000 |  |  |  | 2244524.6 |  | Fully
11 | Construction of Solar Drier (F. Valdevieso, New Bugasong) |  | 300000 |  |  |  | 0 |  | Not Implemented
12 | Rehab of Sitio Kilomawa-Situi Cogon (FMR) @ Sayaran |  | 500000 |  |  |  | 499024.8 |  | Fully
13 | Construction of Solar Drier @ Purok Tanglaw, Sta. Maria |  | 300000 |  |  |  | 299718 |  | Fully
14 | Rehab of Purok Pagkakaisa-Purok Ilomavis (FMR, Sta Maria |  | 300000 |  |  |  | 299421.4 |  | Fully
15 | Concreting of Tamped-Sitio Centro, Taguranao Road 300 mtrs. |  | 4500000 |  |  |  | 4498838.53 |  | Fully
16 | Concreting of Sitio Buguac (Kibia-Latagan Road 300 mtrs. |  | 4500000 |  |  |  | 4493345.01 |  | Fully
17 | Concreting of Pobl;acion-Kidama Road 180 mtrs. |  | 2000000 |  |  |  | 1994968.82 |  | Fully
18 | Concreting of Manuel Roxas Extension 250 mtrs. |  | 3000000 |  |  |  | 2994998 |  | Fully
C | ENVIRONMENTAL MANAGEMENT(9000)
1 | Aid to SLF Operation and Grabage Collections |  | 1100000 |  |  |  | 196240 |  | Partially
2 | Support to reforestation program, projects & activities |  | 63250.2 |  |  |  | 0 |  | Not Implemented
| Total |  | 58113250.2 |  |  |  | 51658745.81
We hereby certify that we have reciewed the contents and hereby attest to
the veracity and correctness of the data or information contained in this
document.
LERIO D. MIGUEL, CPA
Municipal Accountant

## CF-2021
FDP Form 9-Statement of Cash Flows
(BLGF Memorandum Circular No. 09-2012 dated February 21, 2012, Annex 2)
STATEMENT OF CASH FLOWS
4th, Quarter, CY 2021
Province, City or Municipality: North Cotabato, Matalam
Cash Flows from Operating Activities:
Cash Inflows:
| Collections from Taxpayers | 24917862.79
| Share from Internal Revenue Collections | 290566251
| Receipts from Sale of Goods or Services | 7859271.55
| Interest Income | 336403.2
| Dividend Income | 0
| Other Receipts | 39757267.83
| Total Cash Inflow | 363437056.37
Cash Outflows:
| Cash payments for expenses | 2860077.44
| To suppliers/creditors | 181419421.33
| To Employees | 82639818
| Interest Expenses | 9755714.68
| Other Expenses | 31578459.24
| Total Cash Outflow | 308253490.69
| Net Cash from Operating Activities |  |  | 55183565.68
Cash Flows from Investing Activities:
Cash Inflows:
| From Sale of Property, Plant and Equipment | 0
| From Sale of Debt Securities of Other Entities | 0
| From Coll. of Principal on Loans to Other Entities | 0
| Total Cash Inflows | 0
Cash Outflows:
| To Purchase Property, Plant and Equipment | 64572689.55
| To Purchase Debt Securities of Other Entities | 0
| Total Cash Outflow | 64572689.55
| Net Cash from Investing Activities: |  |  | -64572689.55
Cash Flows from Financing Activities
Cash Inflows:
| From Issuance of Debt Securities | 0
| From Acquisition of Loan | 0
| Total Cash Outflow | 0
Cash Outflows:
Retirement/Redemption of Dedt Securities
| Payment of Loan Amortization | 16748288.72
| Total Cash Outflow | -16748288.72
| Net Cash from Financing Activities |  |  | -16748288.72
Net Increase in Cash |  |  |  | -26137412.59
Cash at Beginning of the Period |  |  |  | 394599734.46
Cash at the End of the Period |  |  |  | 368462321.87
We hereby certify that we have reviewed the contents and hereby attest to the veracity and
correctness of the data or information contained in this documents
| LERIO D. MIGUEL, CPA |  | OSCAR M. VALDEVIESO
| Municipal Accountant |  | Municipal Mayor

## sef-util. -2021
FDP Form 11-SEF Utilization
(DepEd-DBM-DILG Circular No. 1 s. 2017, SEF Budget Accountability Form No. 1)
SPECIAL EDUCATION FUND UTILIZATION
4th Quarter, CY 2021
Province/City/Municipality : North Cotabato, Matalam
Receipt from SEF |  | Php | 5923867.55
Less: | DISBURSEMENTS (broken down by expense
class and by object of expenditure)
Personal Services
| Salaries & Wages - Casual |  | 0
Maintenance and Other Operating Expenses
| Office Supplies Expenses |  | 113476
| Medical, Dental and Laboratory Supplies Expenses |  | 141680.25
| Fuel, Oil & Lubricant Expenses |  | 118227.77
| Repair & Maint.- Infrastructure Assets |  | 97945.5
| Donations |  | 699190
| Other Maintenance and Operating Expenses | ` | 97668.76
| Depreciations |  | 448269.47
1716457.75
| Capital Outlay |  | 0
| Financial Expenses |  | 0
Sub-Total |  |  | 1716457.75
Balance |  | Php | 4207409.8
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data
or information contained in this document
| LERIO D. MIGUEL, CPA | OSCAR M. VALDEVIESO
| Municipal Accountant | LCE, Chairman, LSB

## LDRRM
FDP Form 8- Local Disaster Risk Reduction and Management Fund Utilization
(Commission on Audit Form)
LOCAL DISASTER RISK REDUCTION AND MANAGEMENT FUND UTILIZATION
4th Quarter, CY 2021
Province, City or Municipality: NORTH COTABATO, MATALAM
PARTICULARS |  |  | NDRRMF | From Other LGUs | From Other Sources | Total
| Quick Response Fund | Mitigation Fund
| 30% | 70%
A. Sources of Funds
Current Appropriations | 4514643.76 | 10534168.79 |  |  |  | 15048812.55
Continuing Appropriations | 0 | 18198429.28 |  |  |  | 18198429.28
Previous Year's Appropriation transferred to the Special Trust Fund | 2711093.91 | 548567.1 |  |  |  | 3259661.01
CY 2017 | 0 | 0 |  |  |  | 0
CY 2016 | 0 | 0 |  |  |  | 0
CY 2015 | 0 | 0 |  |  |  | 0
Initial Deposit |  | 10000 |  |  |  | 10000
Interest Income |  | 205270.88 |  |  |  | 205270.88
Transfers/Grants | - | - |  | 550000 |  | 550000
Total Funds Available | 7225737.67 | 29496436.05 | 0 | 550000 | 0 | 37272173.72
B. Utilization
2021 | [5 empty] | 0
Construction of Facilities for Flood Control |  | 1290399.62 |  |  |  | 1290399.62
Desilting of Canals, Creeks and Rivers |  | 466745 |  |  |  | 466745
Add'l Riprapping of Creeks @ Sitio Hinigaran, L. Malamote |  | - |  |  |  | 0
Relief of Operating Assistance |  | 73768 |  |  |  | 73768
Capability Development |  | 215846 |  |  |  | 215846
Pre-Disaster Risk Assessment and |  | 7980 |  |  |  | 7980
Rapid Disaster Analysis & Needs Assessment
Information, Education and Campaign |  | 38971.66 |  |  |  | 38971.66
Emergency Medical Supplies and Medicines |  | 216778 |  |  |  | 216778
Support to Agriculture Assistance |  | - |  |  |  | 0
Provision of Livehood Assistance |  | 51597.06 |  |  |  | 51597.06
0
2020 | [5 empty] | 0
Construction of Box Culvert @ P7, W. Patadon |  | 1201857 |  |  |  | 1201857
Desilting of Canals, Creeks and Rivers @ Taguranao |  | 118352 |  |  |  | 118352
0
2019 | [5 empty] | 0
Construction of Drainage Canal @ MH Del Pilar St. |  | 247357 |  |  |  | 247357
Add'l Riprapping of Creeks @ Sitio Hinigaran @ L. Malamote |  | 126200 |  |  |  | 126200
Support of Agricultural Supply to Affected Farmers |  | 763750 |  |  |  | 763750
0
2018 | [5 empty] | 0
Information, Education and Communication |  | 164945 |  |  |  | 164945
0
2017 | [5 empty] | 0
Construction of Drainage Canal @ Tuscano St. |  | 994826.45 |  |  |  | 994826.45
0
Total Utilization | 0 | 5979372.79 | - | 0 | - | 5979372.79
Unutilized Balance | 7225737.67 | 23517063.26 | 0 | 550000 | 0 | 31292800.93
I hereby certify that I have reviewed the contents and hereby attest to the veracity and correctness of data or information contained in this document.
LERIO D. MIGUEL, CPA
Municipal Accountant

## Cash Advance
FDP Form 12 - Unliquidated Cash Advances
UNLIQUIDATED CASH ADVANCES
4th QUARTER, 2021
Province, Cty or Municipality: Matalam
Name of Debtor | Amount Balance | Date Granted | Purpose | Amount Due
|  |  |  | Current |  |  | Past Due
|  |  |  | Less than 30 days | 31-90 days | 91-365 days | Over 1 year | Over 2 years | 3 years and above
Oscar M. Valdevieso | 3859500 | 12/07/21 | Confidential Fund | 3859500
Total | 3859500 |  |  | 3859500 | 0 | 0 | 0 | 0 | 0
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
| LERIO D. MIGUEL, CPA | [5 empty] | OSCAR M. VALDEVIESO
| Municipal Accountant | [5 empty] | Municipal Mayor

## Complement
FDP Form 13-Manpower Complement
MANPOWER COMPLEMENT
Republic of the Philippines
Budget Year 2021/ 4th Quarter
MUNICIPALITY OF MATALAM
Nature of Appointment or Employment | Number of Employees | Annual Compensation and other Benefits |  | Total
1. Permanent | 92 | #N/A | #N/A | #N/A
2. Elective | 12 | #N/A | #N/A | #N/A
3. Co-terminous | 5 | #N/A | #N/A | #N/A
4. Casual | 32 | #N/A | #N/A | #N/A
5. Job Order | 72 | #N/A | #N/A | #N/A
Total | 213 | #N/A | #N/A | #N/A
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information in contained in this document
JERMAINE JOIEE B. TORRES |  | LERIO D. MIGUEL, CPA | OSCAR M. VALDEVIESO
Administrative Officer V |  | Municipal Accountant | Municipal Mayor