## 2021 final
ANNUAL GENDER AND DEVELOPMENT (GAD) ACCOMPLISHMENT REPORT
FY 2021
Region : | REGION XII |  |  |  | Total Budget of LGU: | PHP301,501,251.00
Province: | COTABATO |  |  |  | Total GAD Budget: | PHP 15,075,062.55
City/Municipality: | MATALAM
Gender Issues/ GAD Mandate | GAD Objectives | Relevant LGU P/P/A | GAD Activity | Performance Indicator and Target | Actual Results | Total Approved GAD Budget | Actual Cost or Expenditure | Variance/ Remarks
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9)
Client -Focused GAD Mandate
*MAGNA CARTA OF WOMEN RA 9710 is comprehensive human rights laws that seek to eliminate discrimination against women by recognizing, protecting, fulfilling and promoting the rights of Filipino women especially those in marginalized sector | *To encourage 990 women to attend in all women’s activities | * People Empowerment | * Women’s Month Celebration | * 990 women's attended the Women’s Day Celebration on March 2021 | *The womens celebration was conducted to different barangays namely: Brgy Poblacion, Brgy Kabulacan, Brgy New Alimodian, Brgy Linao, Brgy Kilada and Brgy Bangbang dated on March 09, 18, 19, 25 & 26, 2021 with a total participants of 1141 with 119 male and 1022 female | 400000 | 399790 | 210
Gender Issues/ GAD Mandate | GAD Objectives | Relevant LGU P/P/A | GAD Activity | Performance Indicator and Target | Actual Results | Total Approved GAD Budget | Actual Cost or Expenditure | Variance/ Remarks
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9)
* Lack of proper recognition to 180 female municipal employees | * To recognize, honor, and show appreciation and express love, adoration and gratitude to all mothers | *Support to Mother's Day Celebration | *Conduct Mother’s Day Celebration | * A 180 female municipal employees honored by the month of May 2021 | *A total of 200 with 141 female and 59 male employees were be recognized and honored on May 20, 2021 held at Municipal Gym | 100000 | 99950 | 50
* Lack of proper recognition to 89 male municipal employees | *To recognize, honor, and show appreciation and express love, adoration and gratitude to all fathers | *Support to Father's Day Celebration | * Conduct Father’s Day Celebration | * 89 male municipal employees by the month of June 2021 | *A total of 150 with 110 male and 40 female employees were be recognized and honored on June 24, 2021 held at Municipal Gym | 100000 | 99950 | 50
*Presence of 25 male and 25 female indigent high school and 20 male and 15 female indigent college students | * To ensure continuous schooling of indigent students | * Special Program for Employment of Students (SPES) | * Provision of summer job employment for deserving and qualified indigent students | *25 male and 25 female indigent high school and 20 male and 15 female college indigent students availed the program from March-April 2021 | *A total of 74 indigent college students availed the SPES program where 33 male and 41 female during summer of August-September 2021 | 437580 | 436896 | 684
Gender Issues/ GAD Mandate | GAD Objectives | Relevant LGU P/P/A | GAD Activity | Performance Indicator and Target | Actual Results | Total Approved GAD Budget | Actual Cost or Expenditure | Variance/ Remarks
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9)
*Alarming presence of diseases infected with schistosomiasis among male and female farmers and their children, and thus hampers agricultural productivity | *To Increase case finding and surveillance on endemic barangays | *Disease Control Program | *IEC campaign on the preventive and control treatment of Schistosomiasis Disease *Mass Drug Assessment | * 200 men and 200 women farmers participants from 4 endemic barangays will be given awareness on the preventive measures and control of Schistosomiasis by the month of July 2021 | * Awareness on Schistosomiasis was conducted on October 22, 2021 held at Brgys Taculen, Central Malamote and New Pandan attended by barangay populace with a total participants of 410 where 140 male and 270 female | 50000 | 47000 | 3000
* High incidence of dengue cases, 319 (148 female and 171 male) in 2019 | * To decrease incidence of dengue cases by 80 % in 2021 *To intensify community awareness and participation to successfully minimize or eradicate the dengue disease | *Disease Control Program | *Conduct Anti-Dengue Forum | *15 barangays with dengue cases *200 male and 200 female participants were given IEC/advocacy about dengue diseases by the month of July 2021 | *Anti-Dengue orientation was conducted on October 20, 2021 held at Brgy Kibudoc, Brgy Ilian and Brgy Alimodian attended by 137 male and 278 female with a total participants of 415 | 70000 | 67970 | 2030
* Prevalence of men and women initiated smoking at early age | *To Increase adequate awareness on the effects of smoking | *Anti-Smoking Law Implementation | * Conduct Anti-Smoking Symposium | * 250 female and 250 male high school students at all level attended the symposium by the month of October 2021 | *Anti- Smoking Orientation was conducted at Brgy Salvacion and Brgy Marbel with 96 male and 209 female with a total participants of 305 attended by youth | 70000 | 69195 | 805
Gender Issues/ GAD Mandate | GAD Objectives | Relevant LGU P/P/A | GAD Activity | Performance Indicator and Target | Actual Results | Total Approved GAD Budget | Actual Cost or Expenditure | Variance/ Remarks
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9)
*Prevalence of illegal drug use by young male and female adolescent users | *To educate senior high school students on the prevention and control of dangerous drugs use | *Adolescent Health and Youth Development Program (AHYP) | *Conduct Drug Abuse and Resistance Education (DARE) Program Orientation | * 400 male and 400 female from Grade 11 & 12 students attended the orientation by the month of September 2021 | *DARE orientation was conducted at Brgy Kabulacan and Brgy Sta. Maria attended by youth where 101 male and 104 female with a total participants of 205 attended the said activity last October 21, 2021 | 103000 | 102178 | 822
* Prevalence of HIV/AIDS, Sexually Transmissible Infections (STIs), Teenage Pregnancy and Adolescent-Sexual Reproductive Health (ASRH) | * To educate 1000 senior high school students on HIV/AIDS, Sexually Transmissible Infections (STIs), Teenage Pregnancy and Adolescent-Sexual Reproductive Health (ASRH) in 2021 | * Adolescent Health and Youth Development Program (AHYDP) | * Conduct Continuing IEC/Advocacy Campaign on AHYDP | * 500 male and 500 female senior high school students oriented on HIV/AIDS, Sexually Transmissible Infections (STIs), Teenage Pregnancy and Adolescent-Sexual Reproductive Health (ASRH) by the month of October 2021 | *AHYDP orientation and COVID 19 awareness was conducted at Brgy New Bugasong, Brgy Natutungan, Brgy West Patadon and Brgy Arakan attended by barangay young peoplelast October 2021 with 245 male and 264 female, a total of 509 participants | 110000 | 108394 | 1606
Gender Issues/ GAD Mandate | GAD Objectives | Relevant LGU P/P/A | GAD Activity | Performance Indicator and Target | Actual Results | Total Approved GAD Budget | Actual Cost or Expenditure | Variance/ Remarks
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9)
*Magna Carta of Women RA 9710 is comprehensive human rights laws that seek to eliminate discrimination against women by recognizing, protecting, fulfilling and promoting the rights of Filipino women specially those in marginalized sector | *To disseminate information on the following laws: a. RA 7610-Special Protection of Children against abuse, exploitation and discrimination b. RA 9262-Violence Against Women and their Children c. RA 9208-Anti-Traficking in Person d.RA9344-Juvenile Justice and Welfare Act of 2006 e. RA 9165-Comprehensive Dangerous Drugs Acts of 2002 | *People Empowerment | *Conduct Orientation/ symposium on RA 7610, RA 9262, RA 9208, RA 9344 & RA9165 | * 800 male and female participants from 34 barangays by September 2021 | *A total of 544 where 156 male and 388 female attended the orientation on RA 7610, RA 9262, RA 9208, RA9344 & RA 9165 held at Brgy New Alimodian, Brgy Sta. Maria, Brgy Linao, Brgy Kidama and Brgy Manubuan last November, 20, 21, 22 & 23, 2021 | 187000 | 184470 | 2530
Gender Issues/ GAD Mandate | GAD Objectives | Relevant LGU P/P/A | GAD Activity | Performance Indicator and Target | Actual Results | Total Approved GAD Budget | Actual Cost or Expenditure | Variance/ Remarks
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9)
* Prevalence of HIV/AIDS, Sexually Transmissible Infections (STIs), Teenage Pregnancy and Adolescent-Sexual Reproductive Health (ASRH) | * To increase awareness of senior high school students on threats and risks of adolescence | *Adolescent Health and Youth Program | *Usapang Barkadahan | * 675 male and 675 female senior high school students attended the activity by June-July 2021 | *Usapang Barkadahan was undertaken on November 22-23, 2021 held at Municipal Gym attended by SK officials and out-of-school youthwith a total number of 282 where 124 male and 158 female participated | 150000 | 148890 | 1110
*Limited income opportunities for marginalize men and women below poverty threshold (either PWD, solo parent, youth and family head) | *To capacitate and provide access to livelihood opportunities to marginalize men and women through organized sector | *Livelihood Development Program | *Skills Training for Community Based Food Processing on Tocino | *4 livelihood skills training conducted by 400 families and 200 individuals attended by the month of April-May 2021 | *Skills Training on Tocino was conducted at Brgy West Patadon, Brgy Estado, Brgy Marbel, Brgy Natutungan, Brgy Kidama and Brgy Pinamaton on November 24, 26, 27 &28, 2021 attended by marginalized individuals with a total number of 603 participants composed of 150 male and 453 female as IGP for the benefits of thier families | 256585 | 253986.5 | 2598.5
Gender Issues/ GAD Mandate | GAD Objectives | Relevant LGU P/P/A | GAD Activity | Performance Indicator and Target | Actual Results | Total Approved GAD Budget | Actual Cost or Expenditure | Variance/ Remarks
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9)
* inadequate perception and knowledge on the rights and empowered of cultural minorities | * To increase the level of awareness on the rights of Indigenous People | * People Empowerment | *Conduct IP Month Celebration | * 300 IPs families attended the celebration by the month of October 2021 | *Indigenous Peoples Month Celebration was conducted at Brgy Bato, Brgy Natutungan, Brgy Lampayan and Brgy Ilian on November 16, 17 & 18, 2021 participated by IPs families with a total number of 311 where 117 male and 194 female in attendance | 151400 | 149400 | 2000
* Low capacity of service providers to all 74 female Day Care Workers | *To capacitate the Day Care Workers | * Support to Day Care Workers | * Conduct Day Care Workers Congress | *74 Day Care Workers (Male 0; female 74) attended the Congress by November 2021 | * A total of femlae 74 Day Care Workers attended the Day Care Worker Day Celebration last November 29, 2021 held at Municipal Gym | 170000 | 169211 | 789
Gender Issues/ GAD Mandate | GAD Objectives | Relevant LGU P/P/A | GAD Activity | Performance Indicator and Target | Actual Results | Total Approved GAD Budget | Actual Cost or Expenditure | Variance/ Remarks
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9)
*Low awareness of male and female food handlers on the proper food safety management | * To capacitate food handlers on the proper food safety management | *Proper Food Handling | *Conduct Food Hygiene Training | * 1 training conducted attended by 30 female and 25 male food handlers from meat, fish, vegetables, rice, refreshment, fruits, restaurants and others food owners by the month of December 2021 | *Food handlers owners was oriented on proper food safety on November 23, 2021 held at Municipal Gym with 31 male and 91 female with a total number of participants of 122. Resource Persons from Provincial Government of Cotabato | 60000 | 59750 | 250
*Prevalence of HIV/AIDS, Sexually Transmissible Infections (STIs), Teenage Pregnancy and Adolescent-Sexual Repro-Health (ASRH) | * To educate 1000 senior highs school students on HIV/AIDS, Sexually Transmissible Infections (STIs), Teenage Pregnancy and Adolescent-Sexual Repro-Health (ASRH) | *Health Education and Control of Communicable Disease | * World Aids Day Celebration | *500 male and 500 female senior high school students in 10 public and private schools and Out-of -School Youth (OSY) conducted on 1st week of December 2021 | *Symposium on HIV AIDS and others communicable disease was conducted in lieu with the World Aids Day Celebration held at Municipal gym on December 1, 2021 attended by different individuals with a total number of participants of 559 where 265 male and 294 female participants facilitated by MHO personnel | 200000 | 195940 | 4060
Gender Issues/ GAD Mandate | GAD Objectives | Relevant LGU P/P/A | GAD Activity | Performance Indicator and Target | Actual Results | Total Approved GAD Budget | Actual Cost or Expenditure | Variance/ Remarks
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9)
*Increasing of lifestyle diseases (Hypertension, DM, Kidney disease) of men, women and children regardless of age | * To provide additional knowledge on proper diet and exercise | *Prevention and Management of a Healthy Lifestyle | *Conduct of healthy lifestyle activities | *Medical check up conducted to 250 male and 130 female participants by the month of November 2021 | *Awareness on Healthy Lifestyle and Medical Mission was conducted amongst senior citizens held at Municipal Gym on December 10, 2021 with a total number of 383 where 95 male and 288 female | 120000 | 117948 | 2052
*Inadequate supply of blood and blood products for marginalized men, women and children | *To collect ample supply of safe blood for marginalize men, women and children *Ensure availability of blood for in need patient | * Mass Blood Donation Program | * Conduct of Mass Blood Donation | *Increased number of blood collected of 100% total population * 200 men and 200 women participated in blood donation program from 34 brgys by December 2021 | *Out of 413 where 218 male and 195 female only 158 (105 male, 62 female) are qualified to donate blood. 167 units ample blood was collected from qualified blood donor. The activity was conducted in different barangays last September 09, 23, 29, November 04, 18 and December 13, 2021 held at Brgy Minamaing, Brgy Bato, Brgy Poblacion, Brgy Natutungan, Bargy Sarayan and Municipal Gym with the support of MHO personnel | 154000 | 152340 | 1660
Gender Issues/ GAD Mandate | GAD Objectives | Relevant LGU P/P/A | GAD Activity | Performance Indicator and Target | Actual Results | Total Approved GAD Budget | Actual Cost or Expenditure | Variance/ Remarks
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9)
* Low capacity of 30 male and 15 female Sangguniang Kabataan Officials to maximize and manage their future and become responsible leader of tomorrow | *To capacitate SK Officials by the end of the year | *Adolescent Health and Youth Development Program (AHYDP) | *Conduct Sexually Healthy And Personally Effective Adolescents (SHAPERS) CAMP | *Number of SK Officials/member *30 male and 15 female SK Officials/member attended the 3-day training as pool of trainers by November 2021 | *Forty Five (45) Sangguniang Kabataan officials where 33 male, 12 female attended the SHAPERS Camp held at Municipal Gym on December 15-16, 2021. The activity was facilitated by PGO-Population Division Personnel | 100000 | 99670 | 330
*Limited income opportunities for marginalize men and women below poverty threshold (either PWD, solo parent, youth and family head) | *To capacitate and provide access to livelihood opportunities to marginalize men and women through organized sector | *Livelihood Development Program | *Skills Training for Community Based Food Processing on Chicken & Pork Chorizo | *4 livelihood skills training conducted by 400 families and 200 individuals attended by the month of April-May 2021 | *From Brgy New Pandan, Brgy Dalapitan, Brgy Minamaing, Brgy Sta. Maria and Brgy Taguranao are the beneficaries of Livelihood Skills Training on chicken and Pork Chorizo last December 22, 23, 24 & 26, 2021 wit a total participants of 610 where 228 male and 382 female by TESDA Personnel | 262005 | 259540 | 2465
Gender Issues/ GAD Mandate | GAD Objectives | Relevant LGU P/P/A | GAD Activity | Performance Indicator and Target | Actual Results | Total Approved GAD Budget | Actual Cost or Expenditure | Variance/ Remarks
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9)
*Lack of awareness of pregnant women on the significance of Facility Based Deliveries (FBD) | *To strengthen information, education, communication campaign and counseling on the importance of pre-natal an post-natal care, facility based deliveries to all pregnant women | * Maternal and Child Health Care Program | * Conduct "Buntis Congress" | *250 pregnant women attended the Buntis Congress by the month of October 2021 | *Two Hundred Fifty Two (252) pregnant women attended the Buntis Day from different barangays held at Municipal Gym on December 20, 2021. The participants were provided buntis kit to be used for during their deliveries. | 140000 | 138470 | 1530
*Low awareness of 380 solo parents (44 male & 336 female) on RA8972 | *To Increase awareness of solo parents about RA8972 and to ensure all the benefits and privileges to solo parents will be provided within 2021 | * People Empowerment | * Conduct of orientation on RA 8972 Solo Parent Act | *380 Solo parents with 44 male & 336 female attended the orientation by the month of October 2021 | *A total of 252 where 45 male and 207 female solo parents was the participants during the orientation held at Municipal Gym on December 26, 2021 | 120000.55 | 119000 | 1000.55
Gender Issues/ GAD Mandate | GAD Objectives | Relevant LGU P/P/A | GAD Activity | Performance Indicator and Target | Actual Results | Total Approved GAD Budget | Actual Cost or Expenditure | Variance/ Remarks
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9)
*Low capacity of service providers among 267 female and 1 male Barangay Health Workers who served the barangays | *To capacitate Barangay Health Workers | * Support to Barangay Health Workers (BHW) | * Conduct Barangay Health Workers Capability Building | *268 BHWs (267 Female & 1 Male) attended the training from 34 barangays by the month of November 2021 | *One (1) male and Two Hundred Seventy Three (273) with a total number of 274 BHWs attended the BHWs Day Celebration held at Municipal Gym n December 26, 2021 | 235752 | 233940 | 1812
*Low capacity of service providers ( 77 female and 3 male) BNS | *To capacitate Barangay Nutrition Scholars | *Support to Population and Nutrition Program | *Conduct Training/Seminar/Capability Building/ Congress | *80 BNS (77 Female & 3 male) from 34 brgys attended 2 days capability building by November 2021 | *Barngay Nutrition Scholar Day was conducted on December 26, 2021 held at Municipal Gym with a total number of 70 (3 male, 67 female) BNS | 100000 | 93464 | 6536
*Limited number of male and female farmers /organizations attending CSO’s and PO’s Day Celebration that will give them substantial agricultural information | *To increase attendance of male and female farmers/organization in CSO’s and PO’s Day Celebration | * Civil Society Organizations and Private Organizations Day Celebration | * Conduct Civil Society Organizations and Private Organizations Day Celebration | *At least 350 male and 150 female attended the celebration during Matalam Foundation Anniversary by the month of December 2021 | *There were a convergence celebration of CSOs/POs held at Municipal Gym on December 28, 2021. The activity was attended by 501 farmers participants from different association where 238 male and 263 female was provided by agricultural inputs | 200000 | 198100 | 1900
Gender Issues/ GAD Mandate | GAD Objectives | Relevant LGU P/P/A | GAD Activity | Performance Indicator and Target | Actual Results | Total Approved GAD Budget | Actual Cost or Expenditure | Variance/ Remarks
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9)
*Presence of 68 unwed couples | *Legalized 68 couples at the end of the year | *Mass Wedding Ceremony *Kasalan sa Fiesta | * Conduct Mass Wedding | *Number of unmarried couples living together without solemnity *68 couples, 340 sponsors and 292 guests provided with meals and snacks and souvenirs during Matalam Foundation Anniversary on December 2021 | *Forty (40) would-be couples was solemnized by Hon. Mayor last December 28, 2021 at Municipal Gym with the attendance of 199 principal sponsors, relatives from their respective families where 55 male and 144 female witnessed the wedding ceremony | 293200 | 265351.2 | 27848.8
*Limited awareness of pregnant women on the women’s health risks related to pregnancy, child and health care services | * To intensify health education and promotion program on the quality of maternal and child health care services | * Maternal and Child Health Care Program | * Conduct massive IEC campaign to all pregnant women on maternal and child health care *Promulgate/ Implement Ordinance on birthing and breastfeeding policy | 150 pregnant women oriented and availed quality maternal and child care services by the month of October 2021 *1 Ordinance adopted and full implementation | * A total of 153 pregnant women and lactating mothers were attended the maternal health care orientation held at Municipal Gym last December 30, 2021 | 35000 | 34670 | 330
Gender Issues/ GAD Mandate | GAD Objectives | Relevant LGU P/P/A | GAD Activity | Performance Indicator and Target | Actual Results | Total Approved GAD Budget | Actual Cost or Expenditure | Variance/ Remarks
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9)
*Presence of women, men and children without birth certificate. | *100% of men, women and children are registered before the year end | *Rehistro Para Sa Lahat (Mobile Registration) | *Free Registration of live birth | *Number of unregistered persons *850 registered live births from March-December 2021 | *May-November, Rehistro Para sa Lahat (Mobile Registration) was conducted in 8 barangays namely: Brgy Latagan-154 (65 male, 89 female); Brgy Linao-154 (73 male, 81 female); Brgy Bato-84 (47 male, 37 female); Brgy Sarayan- 245 (103 male, 142 female); Brgy New Alimodian- 223 (107 male, 116 female); Brgy Lampayan-255 (119 male, 136 female); Brgy Tamped- 207 (98 male, 109 female); Brgy Kibia-223 (110 male, 113 female). A total of 1545 PSA negative beneficiries were registered in live births | 200000 | 301275 | 35
Gender Issues/ GAD Mandate | GAD Objectives | Relevant LGU P/P/A | GAD Activity | Performance Indicator and Target | Actual Results | Total Approved GAD Budget | Actual Cost or Expenditure | Variance/ Remarks
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9)
*Presence of 100 unemployed individual (either PWD, Solo Parent, youth and family head) below poverty threshold | *To increase family income of 100 unemployed individual by 20% by the end of the year | *Livelihood Development Program | *Provision of “Kabuhayan Kits” to family members (PWD, solo parent, youth and family head) | *100 unemployed individual increased family income through sustained income generating projects before the end of 1st & 2nd Quarter 2021 | *Kabuhayan Kits by means of groceries was provided to 100 indigent families /individuals whose income is below poverty level threshold | 1000000 | 1000000 | 0.00
* Limited access of marginalized farmers families to various agri-based technologist/ products | * To provide various agricultural assistance and services among marginalized farmers families in more productive and sustainable agriculture | *Support to Agricultural Assistance Program | *Procurement and distribution of various agri inputs and tools, poultry and livestock’s | *150 indigent farmers families beneficiaries availed the agricultural assistance by 1st Quarter 2021 | *150 pcs Stainless Steel Knapsack sprayer, 199 hds of goat, 305 Muscovy Female Ducks, 75 hds Muscovy Male Ducks and 15 sacks Crack Corn were procured and provided to 150 marginalized farmer families last December 2021 | 1500000 | 1500000 | 0.00
*Lack of access on health benefit packages premium to the marginalize men, women and children | *To subsidize medical care and other benefits for marginalized men, women and children | * Social Protection Program | * PHILHEALTH Para sa MASA Program | *Provision of PHILHEALTH insurance coverage to 875 indigent men and women with access to the LGU health programs by January -December 2021 | *875 indigents individuals availed the PHILHEALTH insurance Coverage from January-December 2021 | 2100000 | 2100000 | 0.00
Gender Issues/ GAD Mandate | GAD Objectives | Relevant LGU P/P/A | GAD Activity | Performance Indicator and Target | Actual Results | Total Approved GAD Budget | Actual Cost or Expenditure | Variance/ Remarks
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9)
*Limited access to affordable quality drugs and medicines for marginalized men, women and children | *To provide affordable and quality drugs and medicine for marginalize women, men and children | * Accessibility of Health Programs and Services | * Procurement and distribution of affordable and quality drugs and medicines | *100% provision of drugs and medicines to marginalize women, men and children in health center/RHU by January-December 2021 | *100% of drugs and medicines was purchased and provided to indigent men, women and childred from January-December 2021 | 1500000 | 1500000 | 0.00
*Presence of 250 families in crisis situation | * To ensure availability of financial assistance to 250 families during emergency situation | * Assistance for Individual in Crisis Situation (AICS) Program | *Provision of financial assistance to indigent families | * 250 indigent families provided with cash assistance during emergency situation By January to December 2021 | *278 individuals were given financial and burial assistance during emergency crisis situation from January-December 2021 | 1000000 | 1000000 | 0.00
*Lack of medical equipment’s to be used during the medical check-up for marginalized men, women and children | *To provide medical equipment’s for marginalize men, women and children | * Accessibility of Health Programs and Services | * Procurement of medical equipment’s | *100% purchase of medical equipment’s for marginalize men, women and children for 34 barangays health center by the month of April 2021 | *Various medical equipments was purchased for men , women and children to be used during check -ups at RHU at 4th quarter 2021 | 500000 | 499500 | 500
*Considerable number of households without sanitary toilet for the necessity of men, women and children in barangays and open defecation | * Zero Open Defecation in 2021 | *Environmental Sanitation and Provision of Sanitary Toilet | *Provision of Sanitary Toilet | *95 households provided with toilet bowl by the month of April 2021 | *1018 bgs Cement, 509 toilet bowl, 509 PVC Pipe 4", 509 PVC elbow 4" was provided to household without sanitary toilet last 4th quarter 2021 | 950000 | 949794 | 206
Gender Issues/ GAD Mandate | GAD Objectives | Relevant LGU P/P/A | GAD Activity | Performance Indicator and Target | Actual Results | Total Approved GAD Budget | Actual Cost or Expenditure | Variance/ Remarks
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9)
*Limited opportunity for marginalize men and women jobseekers | *To provide a venue for the jobseekers and agencies for them to meet in one place for employment purposes | *Job Economic Enhancement Program | *Conduct JOBS FAIR | * 55 male and 55 female target applicants availed the activity *1 jobs fair conducted by December 2021 | *Jobs fair was scheduled last December 2021 but due of COVID pandemic and no response to the participating travel agencies it was re-schedule by February 2022 | 60000 | 59770 | 230
*Presence of water and food borne disease | *To decrease occurrence of water and food borne disease | *Environmental Sanitation and Provision of Sanitary Toilet | *Conduct of random water samplings | *Number of BAWASA water source sample tested by January-December 2021 | No water sampling conducted due of unavailability of schedule | 50000 |  | 50,000.00 Not Implemented
*Inadequate knowledge on the equal protection of male and female elementary students against any form of bullying and corporal punishment | * To increase awareness on the protection against any form of bullying and corporal punishment | *Adolescent Health and Youth Development Program (AHYDP) | *Conduct Anti-Bullying and Corporal Punishment Orientation | *10 elementary schools with 200 male and 200 female students attended by Grade 5 & 6 elementary students by the month of July 2021 | The orientation on Anti-Bullying and Corporal Punishment was not conducted in different schools because of COVID 19 pandemic and no face to face classes | 50000 |  | 50,000.00 Not Implemented
* Malnutrition prevalence rate at 8.01 | * To decrease the percentage on malnourish children by 5% | * Support to Nutrition Program | * Conduct IEC on Proper Nutrition on Pregnant Women and Lactating Mother | * 10 clustered barangays with 200 pregnant women/mother attended on July 2021 | * IEC on Proper Nutrition on Pregnant women and Lactating Mother was not undertaken due of pandemic | 50000 |  | 50,000.00 Not Implemented
Gender Issues/ GAD Mandate | GAD Objectives | Relevant LGU P/P/A | GAD Activity | Performance Indicator and Target | Actual Results | Total Approved GAD Budget | Actual Cost or Expenditure | Variance/ Remarks
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9)
*Low awareness of the community on various programs on health and nutrition | *To increase awareness of at least 50% of the community on various programs on health and nutrition | * Support to Nutrition Program | * Conduct of Nutrition Month Celebration Culmination Program | * 34 barangays participated the celebration by 200 female and 50 male conducted on July 2021 | No Nutrition Month Celebration Culmination Program conducted due of time frame schedule | 60000 |  | 60,000.00 Not Implemented
*Lack of motivation for men/married women of reproductive age with unmet need of family planning to become acceptors of Family Planning | *To increase awareness and provide technical information on a range of contraceptive methods | *Support to Family Planning Program | * Conduct Talakayan Series/Usapang Pampamilya | * 500 couples participants of their reproductive Age attended the usapan series from 5 brgys by month of August 2021 | *Talakayan Series /Usapang Pampamilya was not undertaken due of mass vaccination program | 0 |  | 86,000.00 Not Implemented
*High unmet need for family planning by couples and individuals in barangays | *To educate couples in the barangays on responsible parenthood and family planning | *Support to Family Planning Month | *Conduct Responsible Parenthood and Family Planning Orientation | * 500 couples on reproductive age undergone proper parenting orientation on August 2021 | Responsible Parenthood and Family Planning Orientation was not conducted due of mass vaccination program | 50000 |  | 50,000.00 Not Implemented
*Prevalence of teenage pregnancy, pre-marital sex and early marriage | *To decrease teenage pregnancy by 30% at the end of 2021 | *Adolescent Health and Youth Development Program (AHYDP) | *Conduct Getting Along…You and Me ( GAYM) | *250 male and 250 female students from Grade 11 & 12 including their parents attended and educated on sexually transmitted diseases by the month of October 2021 | GAYM was not conducted due of no face to face class because of covid 19 pandemic | 93500 |  | 93,500.00 Not Implemented
Gender Issues/ GAD Mandate | GAD Objectives | Relevant LGU P/P/A | GAD Activity | Performance Indicator and Target | Actual Results | Total Approved GAD Budget | Actual Cost or Expenditure | Variance/ Remarks
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9)
* Lack of proper recognition to 500 male and 500 female teachers for their noble devotion | *To provide recognition, honored and showed appreciation and gratitude for all teachers | *Support to Teacher's Day Celebration | * Conduct Teachers Day Celebration | * 500 male and 500 female teachers recognized and honored at the month of October 2021 | *No Teachers Day Celebration conducted because no face to face class due of covid 19 pandemic | 400000 |  | 400,000.00 Not Implemented
ORGANIZATIONAL-FOCUSED
* Inadequate motivation to level up standard of service among 97 male and 103 female municipal employees | *Equipped personal development of municipal employees | * Capability Building | *Seminar on Leadership, Power and Decision Making rank and file municipal officials and employees | * 100% municipal officials and employees attended the training *97 male & 103 female attended the capability building by November 2021 | *Atotal of 205, 111 male and 94 female municipal employess atended the GAD Capability Building cum christmas Party on December 27, 2021 held at Municipal Gym | 500000 | 491060 | 8940
*Strengthening of the GAD mechanism in the LGU (Rule VI Sec 37;C2 MCW-IRR) | *Fully Operationalize GAD mechanism in the LGU | Gender -Responsive Local Governance | *Conduct Quarterly Meeting of GFPS | *Conduct Quarterly Meeting of GFPS * 4 meetings conducted * 9 male & 7 female GFPS-TWG *5 male & 29 female Barangay GFPS attended the quarterly meeting | Meeting with GFPS-TWG was conducted and attended by 34 members with 20 male and 24 female on September 30, 2021 held at Municipal Gym | 80000 |  | 80,000.00 Budget was utelized from LCE's Budget
Gender Issues/ GAD Mandate | GAD Objectives | Relevant LGU P/P/A | GAD Activity | Performance Indicator and Target | Actual Results | Total Approved GAD Budget | Actual Cost or Expenditure | Variance/ Remarks
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9)
*Strengthening of the VAWC Desk in the LGU (Rule IV Sec 12, D MCW-IRR) | *Empowered VAWC Desk Officers and effectively address VAWC cases in the municipality | *Gender-Responsive Local Governance | *Conduct quarterly meetings of VAWC Desk Officers | * 4 meetings conducted in a year *2 male & 32 female Barangay VAWC Desk Officers January-December 2021 | No VAWC Desk Officers Meeting conducted | 80000 |  | 80,000.00 Not Implemented
*Strengthening of the GAD mechanism in the LGU(Rule VI Sec 37;C2a MCW-IRR) | *Developed/Increased awareness of GFPS on gender related policies and principles and integrating GAD concerns in their plans and programs | Gender -Responsive Local Governance | * Attendance to seminars and workshops for effective planning and budgeting, formulation, implementation and monitoring | *3 female and 2 male TWG- GFPS attended the seminar/Workshops by 2nd -4th Quarter 2021 | No seminars/trainings/ workshops attended because of covid 19 pandemic | 125000 |  | 125,000.00 No Seminar/Trainings Attended
*Pursue and maintain relevant enabling mechanism for GAD mainstreaming (Rule IV Sec 37; Ca MCW-IRR) | *Strengthened GO-PO-NGO partnership to maximize the effectiveness of GAD programs and services. | *Project Implementation Review (PIR) and Planning Workshop | *Assessment and evaluation of GAD projects and activities for CY 2018. * Formulate sectoral development plans, programs and activities for CY 2020 | *8 male and 22 female GADFPS convened during the Project Implementation Review by month of November 2021 | No Project Implementation Review coducted by the GFPS Council due of some members was quarantined | 163730 |  | 163,730.00 Not Implemented
Gender Issues/ GAD Mandate | GAD Objectives | Relevant LGU P/P/A | GAD Activity | Performance Indicator and Target | Actual Results | Total Approved GAD Budget | Actual Cost or Expenditure | Variance/ Remarks
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9)
[5 empty] | TOTAL PHP | 15075062.55 | 13706862.7 | 1368199.8
Prepared by: |  |  |  | Approved by: |  | Date:
JOCELYN S. AMBASAN, MPA |  |  |  | OSCAR M. VALDEVIESO
LLSA II / GFPS Chairperson |  |  |  | Municipal Mayor |  | DD/MM/YEAR