## 20%-2021 (2)
FDP Form 7-20% Component of the IRA Utilization
UTILIZATION OF THE 20% COMPONENT OF IRA FOR DEVELOPMENT PROJECTS
3rd Quarter, CY 2021
Province, City or Municipality: North Cotabato, Matalam
| Program or Project | Location | Total | Date Started | Target | Project Status |  | No. of
|  |  | Cost |  | Completion | % of | Total Cost | Extensions, | Remarks
[5 empty] | Date | Completion | Incurred to Date | if any
A | SOCIAL DEVELOPMENT
1 | Const. of Multi-purpose Covered Court w/ Facilities at Matalam Evacuation Center (COVID 19 related Project) |  | 3200000 |  |  |  | 0
2 | Const. of 1 unit - 2storey Management Office and Quarters w/ facilities (COVID 19 related project @ Evac. Center |  | 4300000 |  |  |  | 0
3 | Const. of Guards' Quarter w/ falities @ Evac. Center |  | 500000 |  |  |  | 0
4 | Aid to Sitio Bubungan Water System @ Linao |  | 150000 |  |  |  | 149885
5 | Const. of Child Development Center @ Latagan |  | 300000 |  |  |  | 0
6 | Aid to Bangbang Water System |  | 400000 |  |  |  | 0
7 | Const. of Multi-purpose Covered Court one (1) span @ Sitio Marva, Taguranao |  | 400000 |  |  |  | 0
B | ECONOMIC DEVELOPMENT (Infra-support)
1 | Loan Repayment (DBP) |  | 22000000 |  |  |  | 19080719.38
2 | Concreting of SLF Road (C.Malamote-Manubuan) 300 mtrs. |  | 3000000 |  |  |  | 2994851.64
3 | Rehab of Pinmaton-Bato (via Layangan) Road |  | 500000 |  |  |  | 499040.3
4 | Rehab of Sarayan-Bato Road |  | 500000 |  |  |  | 498996.3
5 | Rehab of Bato-Taguranao Road |  | 500000 |  |  |  | 499000.7
6 | Rehab of Kulog-Sitio Valdevieso Road |  | 500000 |  |  |  | 499032
7 | Rehab of Kulog-Pulangi Road |  | 500000 |  |  |  | 499005.7
8 | Const. of 1 unit Solar Drier @ Sitio Mamporang, Arakan |  | 300000 |  |  |  | 0
9 | Cpncreting of Latagan-Sitio New Leon Road 150 mtrs. |  | 2250000 |  |  |  | 1305590.98
10 | Concreting of Purok Kaunlaran-Linao Road 150 mtrs. |  | 2250000 |  |  |  | 2244524.6
11 | Construction of Solar Drier (F. Valdevieso, New Bugasong) |  | 300000 |  |  |  | 0
12 | Rehab of Sitio Kilomawa-Situi Cogon (FMR) @ Sayaran |  | 500000 |  |  |  | 499024.8
13 | Construction of Solar Drier @ Purok Tanglaw, Sta. Maria |  | 300000 |  |  |  | 0
14 | Rehab of Purok Pagkakaisa-Purok Ilomavis (FMR, Sta Maria |  | 300000 |  |  |  | 0
15 | Concreting of Tamped-Sitio Centro, Taguranao Road 300 mtrs. |  | 4500000 |  |  |  | 4498838.53
16 | Concreting of Sitio Buguac (Kibia-Latagan Road 300 mtrs. |  | 4500000 |  |  |  | 4493345.01
17 | Concreting of Pobl;acion-Kidama Road 180 mtrs. |  | 2000000 |  |  |  | 1994968.82
18 | Concreting of Manuel Roxas Extension 250 mtrs. |  | 3000000 |  |  |  | 2994998
C | ENVIRONMENTAL MANAGEMENT(9000)
1 | Aid to SLF Operation and Grabage Collections |  | 1100000 |  |  |  | 0
2 | Support to reforestation program, projects & activities |  | 63250.2 |  |  |  | 0
| Total |  | 58113250.2 |  |  |  | 42751821.76
We hereby certify that we have reciewed the contents and hereby attest to
the veracity and correctness of the data or information contained in this
document.
| SAMUEL F. FAELDONIA |  |  |  |  | OSCAR M. VALDEVIESO
| Municipal Budget Officer |  |  |  |  | Municipal Mayor