## 20%-2022(v.2)
| FDP Form 7-20% Component of the IRA Utilization | [21 empty] | FDP Form 7-20% Component of the IRA Utilization | [24 empty] | cx
cx
cx
| UTILIZATION OF THE 20% COMPONENT OF IRA FOR DEVELOPMENT PROJECTS | [21 empty] | UTILIZATION OF THE 20% COMPONENT OF IRA FOR DEVELOPMENT PROJECTS - CONTINUING PROJECTS | [24 empty] | cx
| 3rd Quarter, CY 2022 | [21 empty] | 2nd Quarter, CY 2022 | [24 empty] | cx
cx
| Province, City or Municipality: North Cotabato, Matalam | [21 empty] | Province, City or Municipality: North Cotabato, Matalam | [24 empty] | cx
cx
| Program or Project | Location | Total | Date Started | Target | Contract | Project Status |  | No. of | Balance |  |  | Check No. | Date | Payee | Amount | Due To BIR | Completion at | Remarks |  |  |  | Program or Project | Budget Year | Total | Date Started | Target | Contract | Project Status |  | No. of | Balance |  |  | Check No. | Date | Payee | Amount | Completion at | [8 empty] | cx
|  |  | Cost |  | Completion | Amount | % of | Total Cost | Extensions, |  | Remarks | [13 empty] | Cost |  | Completion | Amount | % of | Total Cost | Extensions, |  | Remarks | [14 empty] | cx
[5 empty] | Date |  | Completion | Incurred to Date | if any | [17 empty] | Date |  | Completion | Incurred to Date | if any | [16 empty] | cx
A | SOCIAL DEVELOPMENT | [20 empty] | A | C | [24 empty] | cx
1 | Installation of Water System at Sitio Pangipasan | Brgy. Lampayan | 300000 |  |  |  | 0% |  |  | 300000 | [11 empty] | B | ECONOMIC DEVELOPMENT (Infra-support) | [24 empty] | cx
2 | Construction of Water System at Purok 1 | Brgy. New Abra | 300000 |  |  |  | 100% | 299563 |  | 437 | Completed | [10 empty] | 1 | Road rehabilitation at Prk Marang - Boundary Pinamaton Road | C.Y. 2019 | [23 empty] | cx
3 | Expansion of Latagan Potable Water System | Brgy. Latagan | 200000 |  |  |  | 0% |  |  | 200000 | [12 empty] | New Alimodian (side 3kms) | [24 empty] | cx
4 | Expansion of Napasaan Potable Water System | Brgy. Kibia | 300000 |  |  |  | 0% |  |  | 300000 | [37 empty] | cx
5 | Construction of 8ft. X 8ft. Reservoir for Potable Water System | Brgy. Linao | 300000 |  |  |  | 87.74% | 263218 |  | 36782 | [37 empty] | cx
6 | Construction of Reservoir for Potable Water System | Brgy. Manupal | 300000 |  |  |  | 0% |  |  | 300000 | [37 empty] | cx
7 | Aid to Improvement of Child Development Center | Brgy. New Abra | 100000 |  |  |  | 99.61% | 99615 |  | 385 | Completed | SD7 | 74246273 | 2022.09.28 | CMC-MPC | 99615 |  |  | Materials purchased | [28 empty] | cx
8 | Aid to Construction of Purok Centro Barangay Health Station | Brgy. Taguranao | 200000 |  |  |  | 99.2% | 198400 |  | 1600 | Completed | SD8 | 74246248 | 2022.08.15 | CMC-MPC | 168320 | [31 empty] | cx
9 | Aid to Renovation of Child Development Center | Brgy. West Patadon | 100000 |  |  |  | 100% | 99865.5 |  | 134.5 | Completed | SD8 | 74246270 | 2022.09.26 | JDL | 30080 | 1611.43 |  | 320L Diesl used for DT | [28 empty] | cx
10 | Aid to Improvement of Multi-Purpose Building | Brgy. Minamaing | 150000 |  |  |  | 100% | 149578.75 |  | 421.25 | Completed |  | 74246245 | 2022.08.10 | CMC-MPC | 149578.75 | [31 empty] | cx
11 | Construction of Potable Water System | Brgy. Kabulacan | 300000 |  |  |  | 0% |  |  | 300000 | [37 empty] | cx
| Sub-total (Social) |  | 2550000 |  |  |  |  | 1110240.25 |  | 1439759.75 | 43.54% | [36 empty] | cx
cx
PPAs for COVID-19 Vaccination (Summary) | [47 empty] | cx
12 | Procurement of COVID-19 Vaccination Supplies |  | 1164600 |  |  |  | 100% | 1163282 |  | 1318 | Completed |  | 74246243 | 2022.08.08 | CMC-MPC | 641490 |  |  | IT and Comm'n Eqpt for COVID-19 Program | [28 empty] | cx
13 | Procurement of COVID-19 Vaccines |  | 10000000 |  |  |  | 5.073% | 507300 |  | 9492700 |  |  | 74246240 | 2022.08.03 | GOLDMAN'S ENTERPRISE | 480123.22 | 27176.78 |  | Medical Supplies for COVID19 PPA | [28 empty] | cx
14 | Monitoring of Vaccines for AEFI |  | 479025 |  |  |  | 99.48% | 476522 |  | 2503 | Completed |  | 74246239 | 2022.08.03 | GOLDMAN'S ENTERPRISE | 450994.04 | 25527.96 |  | Medical Supplies for COVID19 PPA | [28 empty] | cx
15 | Provision of Meals of Health Personnel and Vaccinnee during Vaccination |  | 2500000 |  |  |  | 39.92% | 998000 |  | 1502000 |  |  | 74245249 | 2022.08.18 | ZOELARA'S FOOD HOUSE | 978040 | 19960 | [30 empty] | cx
[10 empty] | 0 | [37 empty] | cx
16 | Internet Subscription Expenses |  | 18000 |  |  |  | 0% |  |  | 18000 | [37 empty] | cx
17 | Provision of Fuel for the Transport of Vaccines and Vaccinee |  | 500000 |  |  |  | 95.08% | 475398.65 |  | 24601.35 |  |  | 74246241 | 2022.08.03 | JDL Gasoline Station | 449930.87 | 25467.78 |  | Fuel consumed for COVID19 PPA |  |  |  | Sub-total (Economic) |  | 0 |  |  |  |  | 0 |  | 0 | [15 empty] | cx
18 | Provision of Storage for COVID-19 Vaccines |  | 100000 |  |  |  | 0% |  |  | 100000 | [37 empty] | cx
19 | Conduct of Information and Education Campaign on COVID-19 Vaccines |  | 181250 |  |  |  | 80.45% | 145813 |  | 35437 | [11 empty] | C | ENVIRONMENTAL MANAGEMENT(9000) | [24 empty] | cx
[7 empty] | #DIV/0! |  |  | 0 |  | COVID-12 | 74246269 | 2022.09.19 | J'GLE Papershoppe and Gen'l Merch | 91685 | 4911.69 |  | TV Set and Portable Speaker | [12 empty] | 0 | [15 empty] | cx
20 | Proper Disposal of Infectious Wastes |  | 509800 |  |  |  | 0% |  |  | 509800 |  | COVID-19 | 74246260 | 2022.09.01 | HARGEN Printing Shop | 53045.44 | 1082.56 |  | Tarps for COVID-19 IEC Materials | [12 empty] | 0 | [15 empty] | cx
21 | Miscellaneous Expenses (Payment for Light and Water Bill of the Vaccination Venue) |  | 24000 |  |  |  | 0% |  |  | 24000 | [12 empty] | Sub-total (Environmental) |  | 0 |  |  |  |  | 0 |  | 0 | [15 empty] | cx
[7 empty] | #DIV/0! |  |  | 0 | [37 empty] | cx
21 | Provision of Honorarium for Medical Doctor Attending to COVID-19 Vaccinees |  | 500000 |  |  |  | 42% | 210000 |  | 290000 | [12 empty] | Total |  | #REF! |  |  |  |  | #REF! |  | #REF! | [15 empty] | cx
[7 empty] | #DIV/0! |  |  | 0 | [37 empty] | cx
23 | Procurement of PPEs for COVID-19 Frontliners |  | 1500000 |  |  |  | 0% |  |  | 1500000 | [12 empty] | We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document. | [24 empty] | cx
24 | Procurement of Rapid Testing Kits and Disinfectants for COVID-19 Response |  | 1000000 |  |  |  | 0% |  |  | 1000000 | [37 empty] | cx
[7 empty] | #DIV/0! |  |  | 0 | [37 empty] | cx
25 | Provision of Food and Medicine Assistance to Quarantined Families due to COVID-19 |  | 5000000 |  |  |  | 0% |  |  | 5000000 | [37 empty] | cx
[7 empty] | #DIV/0! |  |  | 0 | [12 empty] | SAMUEL F. FAELDONIA | [5 empty] | OSCAR M. VALDEVIESO | [18 empty] | cx
| Sub-total (COVID-19 Vaccination Summary) |  | 23476675 |  |  |  |  | 3976315.65 |  | 19500359.35 | 16.94% | [11 empty] | Municipal Budget Officer | [5 empty] | Municipal Mayor | [18 empty] | cx
cx
B | ECONOMIC DEVELOPMENT (Infra-support) | [46 empty] | cx
26 | Construction of F. Valdevieso Solar Dryer | Brgy. New Bugasong | 300000 |  |  |  | 76.32% | 228954 |  | 71046 | 23.68% | [36 empty] | cx
[7 empty] | #DIV/0! | [40 empty] | cx
27 | Construction of D. Almarines Solar Dryer | Brgy. Taguranao | 350000 |  |  |  | 76.6% | 268094 |  | 81906 | 23.4% | ED27 | 74246247 | 2022.08.15 | CMC-MPC | 198594 | [31 empty] | cx
28 | Construction of Kidama Solar Dryer | Brgy. Kidama | 300000 |  |  |  | 0% |  |  | 300000 |  | ED27 | 74246272 | 2022.09.28 | JDL | 69500 | 3723.22 |  | 695L of Diesel used for DT | [28 empty] | cx
29 | Construction of Purok 2 Solar Dryer | Brgy. Manupal | 300000 |  |  |  | 0% |  |  | 300000 | [37 empty] | cx
30 | Construction of Purok 1 Solar Dryer | Brgy. West Patadon | 300000 |  |  |  | 0% | 0 |  | 300000 | [37 empty] | cx
31 | Construction of Purok 4 Solar Dryer | Brgy. West Patadon | 300000 |  |  |  | 0% |  |  | 300000 | [37 empty] | cx
32 | Additional 370Ln.m. Concreting of Kibia-Latagan Road | Kibia-Latagan Road | 4100000 |  |  |  | 100% | 4089916.97 |  | 10083.03 | Completed | [36 empty] | cx
33 | Additional 200Ln.m. Concreting of Linao-Bangbang via Kinilid Road | Brgy. Linao | 2700000 |  |  |  | 100% | 2694444.7 |  | 5555.3 | Completed |  | 74246256 | 2022.08.31 | Huesage Construction | 70755.67 | 4717.05 | [30 empty] | cx
cx
34 | Concreting of 200 Ln.m. Central Malamote-SLF Road | Brgy. Central Malamote | 2200000 |  |  |  | 100% | 2192052.66 |  | 7947.34 | Completed | [36 empty] | cx
35 | Concreting of 200 Ln.m. Dalapitan-New Pandan via Purok Bayabas Road | Brgy. New Pandan | 2200000 |  |  |  | 100% | 2192988.4 |  | 7011.6 | Completed |  | 74246252 | 2022.08.25 | Huesage Construction | 59706.64 | 3980.44 | [30 empty] | cx
cx
36 | Concreting of 200 Ln.m. Central Malamote-Taculen Road | Brgy. Taculen | 2200000 |  |  |  | 100% | 2192855.23 |  | 7144.77 | Completed | [36 empty] | cx
37 | Additional Concreting of 250 Ln.m. Highway-Junction Pinamaton Road | Brgy. Pinamaton | 2800000 |  |  |  | 100% | 0 |  | 2800000 | Completed |  | 74246251 | 2022.08.25 | Huesage Construction | 657916.16 | 0 | [30 empty] | cx
cx
38 | Concreting of 400 Ln.m. Taguranao-Arakan Road | Brgy. Taguranao | 5500000 |  |  |  | 100% | 0 |  | 5500000 | Completed |  | 74246250 | 2022.08.25 | Huesage Construction | 329577.89 | 21971.86 | [30 empty] | cx
39 | Concreting of 200 Ln.m. Lower Malamote-New Pandan Road | Brgy. Lower Malamote | 2250000 |  |  |  | 100% | 2242084.12 |  | 7915.88 | Completed | [36 empty] | cx
cx
40 | Loan Repayment to DBP |  | 25000000 |  |  |  | 40.89% | 10222580.06 |  | 14777419.94 |  |  | 74246253 | 2022.08.25 | DBP | 4187072.18 | 1830134.36 | 18301.34 | [29 empty] | cx
| Sub-total (Economic) |  | 50800000 |  |  |  |  | 26323970.14 |  | 24476029.86 | 51.82% |  |  |  |  | principal | interest | grt | [29 empty] | cx
cx
C | ENVIRONMENTAL MANAGEMENT(9000) | [46 empty] | cx
41 | Aid to SLF Operation and Garbage Collections |  | 1000000 |  |  |  | 58.86% | 588610 |  | 411390 |  |  | 74246268 | 2022.09.19 | JDL | 197795 | 10596.16 |  | Rehab of Cell-1 SLF Site | [28 empty] | cx
42 | Support to Reforestation Program (National Greening and Earth Day) |  | 261629.6 |  |  |  | 0% |  |  | 261629.6 | [37 empty] | cx
| Sub-total (Environmental) |  | 1261629.6 |  |  |  |  | 588610 |  | 673019.6 | 46.65% | [36 empty] | cx
cx
| Total |  | 78088304.6 |  |  |  |  | 31999136.04 |  | 46089168.56 | 40.98% | [36 empty] | cx
cx
| We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document. | [46 empty] | cx
cx
cx
cx
| SAMUEL F. FAELDONIA | [5 empty] | OSCAR M. VALDEVIESO | [40 empty] | cx
| Municipal Budget Officer | [5 empty] | Municipal Mayor | [40 empty] | cx
cx
cx
cx
cx
cx
cx
cx
cx
cx
cx
cx
cx
cx
cx
cx
cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx |  | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx
| FDP Form 7-20% Component of the IRA Utilization | [21 empty] | FDP Form 7-20% Component of the IRA Utilization | [24 empty] | cx
cx
cx
| UTILIZATION OF THE 20% COMPONENT OF IRA FOR DEVELOPMENT PROJECTS | [21 empty] | UTILIZATION OF THE 20% COMPONENT OF IRA FOR DEVELOPMENT PROJECTS - CONTINUING PROJECTS | [24 empty] | cx
| For the Calendar Year Ending December 31, 2022 | [21 empty] | 2nd Quarter, CY 2022 | [24 empty] | cx
cx
| Province, City or Municipality: North Cotabato, Matalam | [21 empty] | Province, City or Municipality: North Cotabato, Matalam | [24 empty] | cx
cx
| Program or Project | Location | Total | Date Started | Target | Contract | Project Status |  | No. of | Balance |  |  | Check No. | Date | Payee | Amount | Due To BIR | Completion at | Remarks |  |  |  | Program or Project | Budget Year | Total | Date Started | Target | Contract | Project Status |  | No. of | Balance |  |  | Check No. | Date | Payee | Amount | Completion at | [8 empty] | cx
|  |  | Cost |  | Completion | Amount | % of | Total Cost | Extensions, |  | Remarks | [13 empty] | Cost |  | Completion | Amount | % of | Total Cost | Extensions, |  | Remarks | [14 empty] | cx
[5 empty] | Date |  | Completion | Incurred to Date | if any | [17 empty] | Date |  | Completion | Incurred to Date | if any | [16 empty] | cx
A. | SOCIAL DEVELOPMENT | [20 empty] | A | C | [24 empty] | cx
1 | Installation of Water System at Sitio Pangipasan | Brgy. Lampayan | 300000 |  |  |  | 0% |  |  | 300000 | [11 empty] | B | ECONOMIC DEVELOPMENT (Infra-support) | [24 empty] | cx
2 | Construction of Water System at Purok 1 | Brgy. New Abra | 300000 |  |  |  | 100% | 299563 |  | 437 | Completed | [10 empty] | 1 | Road rehabilitation at Prk Marang - Boundary Pinamaton Road | C.Y. 2019 | [23 empty] | cx
3 | Expansion of Latagan Potable Water System | Brgy. Latagan | 200000 |  |  |  | 0% |  |  | 200000 | [12 empty] | New Alimodian (side 3kms) | [24 empty] | cx
4 | Expansion of Napasaan Potable Water System | Napasaan, Brgy. Kibia | 300000 |  |  |  | 84.56% | 253670 |  | 46330 |  |  | 74246293 | 2022-10-26 | CMC-MPC | 253670 | [31 empty] | cx
5 | Construction of 8ft. X 8ft. Reservoir for Potable Water System | Brgy. Linao | 300000 |  |  |  | 87.74% | 263218 |  | 36782 | [37 empty] | cx
6 | Construction of Reservoir for Potable Water System | Brgy. Manupal | 300000 |  |  |  | 0% |  |  | 300000 | [37 empty] | cx
7 | Aid to Improvement of Child Development Center | Brgy. New Abra | 100000 |  |  |  | 99.61% | 99615 |  | 385 | Completed | [36 empty] | cx
8 | Aid to Construction of Purok Centro Barangay Health Station | Brgy. Taguranao | 200000 |  |  |  | 99.2% | 198400 |  | 1600 | Completed | [36 empty] | cx
9 | Aid to Renovation of Child Development Center | Brgy. West Patadon | 100000 |  |  |  | 100% | 99865.5 |  | 134.5 | Completed | [36 empty] | cx
10 | Aid to Improvement of Multi-Purpose Building | Brgy. Minamaing | 150000 |  |  |  | 100% | 149578.75 |  | 421.25 | Completed | [36 empty] | cx
11 | Construction of Potable Water System | Brgy. Kabulacan | 300000 |  |  |  | 0% |  |  | 300000 | [37 empty] | cx
| Sub-total (Social) |  | 2550000 |  |  |  |  | 1363910.25 |  | 1186089.75 | 53.49% | [36 empty] | cx
cx
PPAs for COVID-19 Vaccination (Summary) | [47 empty] | cx
12 | Procurement of COVID-19 Vaccination Supplies |  | 1164600 |  |  |  | 100% | 1163282 |  | 1318 | Completed | [36 empty] | cx
| Procurement of COVID-19 Vaccines | [9 empty] | Reprogrammed | [36 empty] | cx
14 | Monitoring of Vaccines for AEFI |  | 479025 |  |  |  | 99.48% | 476522 |  | 2503 | Completed | [36 empty] | cx
15 | Provision of Meals of Health Personnel and Vaccinnee during Vaccination |  | 2500000 |  |  |  | 99.8% | 2495000 |  | 5000 | [37 empty] | cx
[10 empty] | 0 | [37 empty] | cx
16 | Internet Subscription Expenses |  | 18000 |  |  |  | 0% |  |  | 18000 | [37 empty] | cx
17 | Provision of Fuel for the Transport of Vaccines and Vaccinee |  | 500000 |  |  |  | 95.08% | 475398.65 |  | 24601.35 | [5 empty] | -22450 | [6 empty] | Sub-total (Economic) |  | 0 |  |  |  |  | 0 |  | 0 | [15 empty] | cx
18 | Provision of Storage for COVID-19 Vaccines |  | 100000 |  |  |  | 0% |  |  | 100000 | [37 empty] | cx
19 | Conduct of Information and Education Campaign on COVID-19 Vaccines |  | 181250 |  |  |  | 87.27% | 158173 |  | 23077 |  |  |  | 84269620 | HARGEN PRINTING | 12360 | [5 empty] | C | ENVIRONMENTAL MANAGEMENT(9000) | [24 empty] | cx
[7 empty] | #DIV/0! |  |  | 0 | [21 empty] | 0 | [15 empty] | cx
20 | Proper Disposal of Infectious Wastes |  | 509800 |  |  |  | 99.51% | 507300 |  | 2500 | [21 empty] | 0 | [15 empty] | cx
21 | Miscellaneous Expenses (Payment for Light and Water Bill of the Vaccination Venue) |  | 24000 |  |  |  | 37.2% | 8929 |  | 15071 |  |  | edfpay.11-014 |  | Concepcion, Wendee | 6000 | [6 empty] | Sub-total (Environmental) |  | 0 |  |  |  |  | 0 |  | 0 | [15 empty] | cx
[7 empty] | #DIV/0! |  |  | 0 |  |  | edfpay.11-015 |  | Quimco, Irvin | 36000 | [31 empty] | cx
21 | Provision of Honorarium for Medical Doctor Attending to COVID-19 Vaccinees |  | 500000 |  |  |  | 99.6% | 498000 |  | 2000 |  |  | edfpay.11-017 |  | Pinto, Jo Ann | 42000 | [6 empty] | Total |  | #REF! |  |  |  |  | #REF! |  | #REF! | [15 empty] | cx
[7 empty] | #DIV/0! |  |  | 0 |  |  | edfpay.11-018 |  | Mulato, Pebbles | 48000 | [31 empty] | cx
23 | Procurement of PPEs for COVID-19 Frontliners |  | 1500000 |  |  |  | 0% |  |  | 1500000 |  |  | edfpay.11-020 |  | Mulato, Pebbles | 48000 | [6 empty] | We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document. | [24 empty] | cx
24 | Procurement of Rapid Testing Kits and Disinfectants for COVID-19 Response |  | 1000000 |  |  |  | 0% |  |  | 1000000 |  |  | edfpay.11-023 |  | Pinto, Jo Ann | 51000 | [31 empty] | cx
[7 empty] | #DIV/0! |  |  | 0 |  |  | edfpay.11-024 |  | Quimco, Irvin | 57000 | [31 empty] | cx
| Provision of Food and Medicine Assistance to Quarantined Families due to COVID-19 | [9 empty] | Reprogrammed | [36 empty] | cx
| Sub-total (COVID-19 Vaccination Summary) |  | 8476675 |  |  |  |  | 5782604.65 |  | 2694070.35 | 68.22% | [11 empty] | SAMUEL F. FAELDONIA | [5 empty] | OSCAR M. VALDEVIESO | [18 empty] | cx
[23 empty] | Municipal Budget Officer | [5 empty] | Municipal Mayor | [18 empty] | cx
B. | ECONOMIC DEVELOPMENT (Infra-support) | [46 empty] | cx
26 | Construction of F. Valdevieso Solar Dryer | Brgy. New Bugasong | 300000 |  |  |  | 76.32% | 228954 |  | 71046 | 23.68% | [36 empty] | cx
[7 empty] | #DIV/0! | [40 empty] | cx
27 | Construction of D. Almarines Solar Dryer | Brgy. Taguranao | 350000 |  |  |  | 76.6% | 268094 |  | 81906 | 23.4% | [36 empty] | cx
28 | Construction of Kidama Solar Dryer | Brgy. Kidama | 300000 |  |  |  | 99.43% | 298282 |  | 1718 | 0.5727% | [36 empty] | cx
29 | Construction of Purok 2 Solar Dryer | Brgy. Manupal | 300000 |  |  |  | 0% |  |  | 300000 |  |  | 74246289 | 2022-10-12 | JDL | 30323.57 | 1716.43 | [30 empty] | cx
30 | Construction of Purok 1 Solar Dryer | Brgy. West Patadon | 300000 |  |  |  | 75.55% | 226662 |  | 73338 |  |  | EDFPAY.12-026 |  | Jestoni Pagador, et.al. | 71800 | [31 empty] | cx
31 | Construction of Purok 4 Solar Dryer | Brgy. West Patadon | 300000 |  |  |  | 75.55% | 226662 |  | 73338 |  |  | 74246285 | 2022-10-10 | JDL | 30493.93 | 1726.07 |  | Fuel Consumed for the PPA | [28 empty] | cx
32 | Additional 370Ln.m. Concreting of Kibia-Latagan Road | Kibia-Latagan Road | 4100000 |  |  |  | 100% | 4089916.97 |  | 10083.03 | Completed |  | 74246290 | 2022-10-12 | JDL | 30493.93 | 1726.07 |  | Fuel Consumed for the PPA | [28 empty] | cx
33 | Additional 200Ln.m. Concreting of Linao-Bangbang via Kinilid Road | Brgy. Linao | 2700000 |  |  |  | 100% | 2694444.7 |  | 5555.3 | Completed | [36 empty] | cx
cx
34 | Concreting of 200 Ln.m. Central Malamote-SLF Road | Brgy. Central Malamote | 2200000 |  |  |  | 100% | 2192052.66 |  | 7947.34 | Completed | [36 empty] | cx
35 | Concreting of 200 Ln.m. Dalapitan-New Pandan via Purok Bayabas Road | Brgy. New Pandan | 2200000 |  |  |  | 100% | 2192988.4 |  | 7011.6 | Completed | [36 empty] | cx
cx
36 | Concreting of 200 Ln.m. Central Malamote-Taculen Road | Brgy. Taculen | 2200000 |  |  |  | 100% | 2192855.23 |  | 7144.77 | Completed | [36 empty] | cx
37 | Additional Concreting of 250 Ln.m. Highway-Junction Pinamaton Road | Brgy. Pinamaton | 2800000 |  |  |  | 100% | 2794743.1305 |  | 5256.8695 | Completed | [36 empty] | cx
cx
38 | Concreting of 400 Ln.m. Taguranao-Arakan Road | Brgy. Taguranao | 5500000 |  |  |  | 100% | 5492219 |  | 7781 | Completed | [36 empty] | cx
39 | Concreting of 200 Ln.m. Lower Malamote-New Pandan Road | Brgy. Lower Malamote | 2250000 |  |  |  | 100% | 2242084.12 |  | 7915.88 | Completed | [36 empty] | cx
cx
40 | Loan Repayment to DBP |  | 25000000 |  |  |  | 96.78% | 24195739.1 |  | 804260.9 | [37 empty] | cx
| Sub-total (Economic) |  | 50800000 |  |  |  |  | 49335697.3105 |  | 1464302.6895 | 97.12% |  | 84269619 | 2023-12-13 | DBP | [32 empty] | cx
cx
C. | ENVIRONMENTAL MANAGEMENT(9000) | [46 empty] | cx
41 | Aid to SLF Operation and Garbage Collections |  | 1000000 |  |  |  | 58.86% | 588610 |  | 411390 | [37 empty] | cx
42 | Support to Reforestation Program (National Greening and Earth Day) |  | 261629.6 |  |  |  | 0% |  |  | 261629.6
| Sub-total (Environmental) |  | 1261629.6 |  |  |  |  | 588610 |  | 673019.6 | 46.65%
D. | 2022 REPROGRAMMING
1 | Support to COVID-19 Vaccination Program |  | 4000000 |  |  |  | 91.81% | 3672434 |  | 327566
2 | Rehabilitation of RHU Building used as Vaccination Center |  | 1500000 |  |  |  | 66.43% | 996474.75 |  | 503525.25
3 | Construction of 3-Chamber COVID-19 Septic Vault |  | 500000 |  |  |  | 99.95% | 499757.5 |  | 242.5 | Completed
4 | Procurement of 6-Wheeler Mini-Dumptruck for Biodegradable Waste Collection |  | 1500000 |  |  |  |  | 1490000 |  | 10000 | Completed
5 | Rehabilitation of Municipal Roads |  | 2500000 |  |  |  | 90.73% | 2268222.15 |  | 231777.85 | [37 empty] | cx
6 | Concreting of Add'l 300LM Kibia-Latagan Rd, Natipakan Rd Section | Brgy. Kibia-Latagan | 5000000 |  |  |  | 14.99% | 749481.06 |  | 4250518.94 | [37 empty] | cx
| Sub-total (2022 Reprogramming) |  | 15000000 |  |  |  |  | 9676369.46 |  | 5323630.54 | 64.51% | [36 empty] | cx
cx
| Grand Total |  | 78088304.6 |  |  |  | 85.48% | 66747191.6705 |  | 11341112.9295 | 85.48% | [36 empty] | cx
cx
| We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document. | [46 empty] | cx
cx
cx
cx
| SAMUEL F. FAELDONIA | [5 empty] | OSCAR M. VALDEVIESO | [40 empty] | cx
| Municipal Budget Officer | [5 empty] | Municipal Mayor | [40 empty] | cx
cx
cx
cx
cx
[13 empty] | EDFPAY.12-027 |  | Cash Incentives - CVID Vaccinees | 500000 | [31 empty] | cx
D | 2022 REPROGRAMMING | [10 empty] | 1 | 84269630 | 2023-12-28 | JDL | 1497734 | [31 empty] | cx
1 | Support to COVID-19 Vaccination Program |  | 4000000 |  |  |  | 69.25% | 2769884 |  | 1230116 |  | 1 | 84269617 | 2023-12-07 | J'GLE - Riso Print | 22450 | [31 empty] | cx
2 | Rehabilitation of RHU Building used as Vaccination Center |  | 1500000 |  |  |  | 66.43% | 996474.75 |  | 503525.25 |  | 1 | 84269605 | 2022-11-17 | ZOELARA | 146706 | 2994
3 | Construction of 3-Chamber COVID-19 Septic Vault |  | 500000 |  |  |  | 99.95% | 499757.5 |  | 242.5 | Completed | 1 | EDFPAY.11-001 |  | Cash Incentives - CVID Vaccinees | 500000
4 | Procurement of 6-Wheeler Mini-Dumptruck for Biodegradable Waste Collection |  | 1500000 |  |  |  |  | 1490000 |  | 10000 | Completed |  | EDFPAY.11-011 |  | Cash Incentives - CVID Vaccinees | 100000
5 | Rehabilitation of Municipal Roads |  | 2500000 |  |  |  | 90.73% | 2268222.15 |  | 231777.85 |  |  | 84269622 | 2023-12-15 | GOLDMAN'S Supply | 1490000
6 | Concreting of Add'l 300LM Kibia-Latagan Rd, Natipakan Rd Section | Brgy. Kibia-Latagan | 5000000 |  |  |  | 14.99% | 749481.06 |  | 4250518.94 |  | 5 | 74246294 | 2022-11-02 | JDL | 186160
[12 empty] | 6 | 74246292 | 2022-10-18 | HUESAGE | 749481.06 | [31 empty] | cx
[12 empty] | 5 | 84269602 | 2022-11-16 | JDL | 128752.15
[12 empty] | 5 | 84269608 | 2022-11-28 | JDL | 113400
| Sub-total |  | 15000000 |  |  |  |  | 8773819.46 |  | 6226180.54 | 58.49% | 5 | 84269611 | 2023-12-01 | JDL | 198690
[12 empty] | 5 | 84269628 | 2023-12-28 | JDL | 142667 | [31 empty] | cx
[12 empty] | 5 | 84269629 | 2023-12-28 | JDL | 142400 | [31 empty] | cx
E. | 2018-2021 EDF BALANCES REPROGRAMMING | [10 empty] | 5 | 84269631 | 2023-12-28 | JDL | 192685 | [31 empty] | cx
1 | Palay Marketing Assistance Program for Legislators and LGUs | National Food Authority | 1000000 |  |  |  | 100% | 1000000 |  | 0 |  | 5 | 84269632 | 2023-12-28 | JDL | 196868 | [31 empty] | cx
2 | Rabies Vaccination Program |  | 560991.3 |  |  |  | 0% | 0 |  | 560991.3 |  | 5 | 84269633 | 2023-12-28 | JDL | 966600
[13 empty] | 84269621 | 2023-12-15 | NFA | 1000000 | [31 empty] | cx
| Sub-total |  | 1560991.3 |  |  |  |  | 1000000 |  | 560991.3 | 64.06%
cx
cx
cx
cx
cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | [36 empty] | cx
[18 empty] | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx
[12 empty] | cx | cx | cx | cx | cx
Note on B5: RJGJ:
Note on B109: RJGJ:
Note on I156: RJGJ: DBP-74246224 Dtd: Jun 21, 2022
Note on I181: RJGJ: As per Norylyn monitoring