## 20%-2023
[29 empty] | x | [38 empty] | cx
FDP Form 7-20% Component of the IRA Utilization | [14 empty] | FDP Form 7-20% Component of the IRA Utilization | [13 empty] | x | [38 empty] | cx
[29 empty] | x | [38 empty] | cx
UTILIZATION OF THE 20% COMPONENT OF IRA FOR DEVELOPMENT PROJECTS | [14 empty] | UTILIZATION OF THE 20% COMPONENT OF IRA FOR DEVELOPMENT PROJECTS (CY 2022) | [13 empty] | x | [38 empty] | cx
As of the 4th Quarter, Calendar Year Ending December 31, 2023 | [14 empty] | As of the 3rd Quarter, Calendar Year Ending December 31, 2023 | [13 empty] | x | [38 empty] | cx
| REGION: XII - SOCCSKSARGEN CALENDAR YEAR: 2023 | [27 empty] | x | [38 empty] | cx
PROVINCE: COTABATO PROVINCE QUARTER: 4
CITY/MUNICIPALITY: MATALAM
[29 empty] | x | [38 empty] | cx
| Program/Project/Activity | Implementing | Location | Total | Date Started | Target | Contract | Project Status |  | No. of | Balance |  |  |  | Program or Project | Location | Total | Date Started | Target | Contract | Project Status |  |  | No. of | Balance |  |  |  | x | [38 empty] | cx
|  | Office/Dept. |  | Cost |  | Completion | Amount | % of | Total Cost | Extensions, |  | Remarks |  |  |  |  | Cost |  | Completion | Amount | % of | Total Cost | Balance | Extensions, |  | Remarks |  |  | x | [38 empty] | cx
[6 empty] | Date |  | Completion | Incurred to Date | if any |  | Completed | [6 empty] | Date |  | Completion | Incurred to Date |  | if any |  |  |  |  | x | [38 empty] | cx
A. | SOCIAL DEVELOPMENT | [12 empty] | A. | SOCIAL DEVELOPMENT | [13 empty] | x | [38 empty] | cx
1 | Support to COVID-19 Vaccination Program | MMO/MHO/MPDO |  | 5000000 |  |  |  | 0% | 0 |  | 5000000 |  |  | 1 | Installation of Water System at Sitio Pangipasan | Brgy. Lampayan | 300000 |  |  |  | 99.48% | 298430 | 1570 |  | 1570 | Completed |  |  | x | [38 empty] | cx
2 | Rehabilitation of Child Dev't Center | MMO/MEO/MPDO | Brgy. Sarayan | 100000 |  |  |  | 98.86% | 98863 |  | 1137 | Completed |  | 2 | Construction of Water System at Purok 1 | Brgy. New Abra | 300000 |  |  |  | 100% | 299563 | 437 |  | 437 | Completed |  |  | x | [38 empty] | cx
3 | Completion of Child Dev't Center | MMO/MEO/MPDO | S. Langka, Brgy. Taguranao | 100000 |  |  |  | 0% | 0 |  | 100000 |  |  | 3 | Expansion of Latagan Potable Water System | Brgy. Latagan | 200000 |  |  |  | 98.19% | 196374 | 3626 |  | 3626 | Completed |  |  | x | [38 empty] | cx
4 | Electrification of LGU Housing for Indigenous People | MMO/MEO/MPDO |  | 400000 |  |  |  | 0% | 0 |  | 400000 |  |  | 4 | Expansion of Napasaan Potable Water System | Napasaan, Brgy. Kibia | 300000 |  |  |  | 84.56% | 253670 | 46330 |  | 46330 |  |  |  | x | [38 empty] | cx
| Sub-total (Social) |  |  | 5600000 |  |  |  | 1.765% | 98863 |  | 5501137 |  |  | 5 | Construction of 8ft. X 8ft. Reservoir for Potable Water System | Brgy. Linao | 300000 |  |  |  | 87.74% | 263218 | 36782 |  | 36782 |  |  |  | x | [38 empty] | cx
[14 empty] | 6 | Construction of Reservoir for Potable Water System | Brgy. Manupal | 300000 |  |  |  | 100% | 295610.5 | 4389.5 |  | 4389.5 |  |  |  | x | [38 empty] | cx
B. | ECONOMIC DEVELOPMENT (Infra-support) | [12 empty] | 7 | Aid to Improvement of Child Development Center | Brgy. New Abra | 100000 |  |  |  | 99.61% | 99615 | 385 |  | 385 | Completed |  |  | x | [38 empty] | cx
1 | Loan Repayment (Concreting of Roads) | MPDO/MEO |  | 25000000 |  |  |  | 92.46% | 23115620.1 |  | 1884379.9 | Completed |  | 8 | Aid to Construction of Purok Centro Barangay Health Station | Brgy. Taguranao | 200000 |  |  |  | 99.2% | 198400 | 1600 |  | 1600 | Completed |  |  | x | [38 empty] | cx
2 | Const'n of Solar Dryer with Warehouse | MPDO/MEO | Brgy. New Abra | 500000 |  |  |  | 0% | 0 |  | 500000 |  |  | 9 | Aid to Renovation of Child Development Center | Brgy. West Patadon | 100000 |  |  |  | 100% | 99865.5 | 134.5 |  | 134.5 | Completed |  |  | x | [38 empty] | cx
3 | Construction of 1 Unit Solar Dryer | MPDO/MEO | Brgy. Bato | 400000 |  |  |  | 99.38% | 397535 |  | 2465 | Completed |  | 10 | Aid to Improvement of Multi-Purpose Building | Brgy. Minamaing | 150000 |  |  |  | 100% | 149578.75 | 421.25 |  | 421.25 | Completed |  |  | x | [38 empty] | cx
4 | Construction of 1 Unit Solar Dryer | MPDO/MEO | P.2, Brgy. Sarayan | 350000 |  |  |  | 71.89% | 251626 |  | 98374 | On-progress |  | 11 | Construction of Potable Water System | Brgy. Kabulacan | 300000 |  |  |  | 99.33% | 298000 | 2000 |  | 2000 | Completed |  |  | x | [38 empty] | cx
5 | Construction of 1 Unit Solar Dryer | MPDO/MEO | P.New Bacolod, Minamaing | 350000 |  |  |  | 71.89% | 251626 |  | 98374 | On-progress |  |  | Sub-total (Social) |  | 2550000 |  |  |  |  | 2452324.75 | 97675.25 |  | 97675.25 | 96.17% |  |  | x | [38 empty] | cx
6 | Construction of 1 Unit Solar Dryer | MPDO/MEO | P.5, Brgy. Kidama | 300000 |  |  |  | 75.6% | 226805 |  | 73195 | On-progress | [16 empty] | x | [38 empty] | cx
7 | Construction of 1 Unit Solar Dryer | MPDO/MEO | P.1, Brgy. W. Patadon | 300000 |  |  |  | 75.57% | 226716 |  | 73284 | On-progress |  | PPAs for COVID-19 Vaccination (Summary) | [8 empty] | 0 | [5 empty] | x | [38 empty] | cx
8 | Concreting of Add'l 200LM C. Malamote-SLF Rd. | MPDO/MEO | Brgy. C. Malamote | 3000000 |  |  |  | 100% | 2992769.97 |  | 7230.03 | Completed |  | 12 | Procurement of COVID-19 Vaccination Supplies |  | 1164600 |  |  |  | 100% | 1163282 | 1318 |  | 1318 | Completed |  |  | x | [38 empty] | cx
[15 empty] | Procurement of COVID-19 Vaccines | [7 empty] | 0 |  |  | Reprogrammed |  |  | x | [38 empty] | cx
9 | Concreting of 200LM Kabulacan-N. Tigbauan Rd. | MPDO/MEO | Brgy. Kabulacan | 3000000 |  |  |  | 100% | 2991998.28 |  | 8001.72 | Completed |  | 14 | Monitoring of Vaccines for AEFI |  | 479025 |  |  |  | 99.48% | 476522 | 2503 |  | 2503 | Completed |  |  | x | [38 empty] | cx
10 | Concreting of Add'l 200LM Kibia-Latagan (Orchid Farm) Rd. | MPDO/MEO | Brgy. Kibia | 3200000 |  |  |  | 100% | 2992000.36 |  | 207999.64 | Completed |  | 15 | Provision of Meals of Health Personnel and Vaccinnee during Vaccination |  | 2500000 |  |  |  | 99.8% | 2495000 | 5000 |  | 5000 |  |  |  | x | [38 empty] | cx
[8 empty] | #DIV/0! | [14 empty] | 0 |  | 0 |  |  |  | x | [38 empty] | cx
11 | Concreting of Add'l 300LM Bangbang-Linao Rd. | MPDO/MEO | Brgy. Bangbang | 4800000 |  |  |  | 100% | 4792227.92 |  | 7772.08 | Completed |  | 16 | Internet Subscription Expenses |  | 18000 |  |  |  | 0% |  | 18000 |  | 18000 |  |  |  | x | [38 empty] | cx
12 | Concreting of 200LM Nat'l Hi-way-Closed Dumpsite | MPDO/MEO | Brgy. Manubuan | 3000000 |  |  |  | 95.26% | 2857671.24 |  | 142328.76 | On-progress |  | 17 | Provision of Fuel for the Transport of Vaccines and Vaccinee |  | 500000 |  |  |  | 95.08% | 475398.65 | 24601.35 |  | 24601.35 |  |  |  | x | [38 empty] | cx
13 | Concreting of 200LM C. Malamote-N. Bugasong via. F. Valdeviso Rd. | MPDO/MEO | Brgy. N. Bugasong | 3000000 |  |  |  | 100% | 2996482.069 |  | 3517.931 | Completed |  | 18 | Provision of Storage for COVID-19 Vaccines |  | 100000 |  |  |  | 0% |  | 100000 |  | 100000 |  |  |  | x | [38 empty] | cx
14 | Concreting of 300LM Sarayan-Bato Rd. | MPDO/MEO | Brgy. Sarayan | 5100000 |  |  |  | 91.45% | 4663915.8065 |  | 436084.1935 | On-progress |  | 19 | Conduct of Information and Education Campaign on COVID-19 Vaccines |  | 181250 |  |  |  | 87.27% | 158173 | 23077 |  | 23077 |  |  |  | x | [38 empty] | cx
15 | Concreting of 200LM Taguranao-Arakan Rd. (S. Centro Section) | MPDO/MEO | Brgy. Taguranao | 3400000 |  |  |  | 100% | 3395319.074 |  | 4680.926 | Completed | [8 empty] | #DIV/0! |  | 0 |  | 0 |  |  |  | x | [38 empty] | cx
16 | Concreting of Add'l 200LM Tamped-Taguranao Rd. | MPDO/MEO | Brgy. Tamped | 3400000 |  |  |  | 100% | 3395956.6475 |  | 4043.3525 | Completed |  | 20 | Proper Disposal of Infectious Wastes |  | 509800 |  |  |  | 99.51% | 507300 | 2500 |  | 2500 |  |  |  | x | [38 empty] | cx
17 | Rehab. of Purok 9, Sitio Eba, Sarayan-Sitio Migcuan, N. Alimodian Rd. | MPDO/MEO | Brgy. Sarayan | 300000 |  |  |  | 100% | 299521.5 |  | 478.5 | Completed |  | 21 | Miscellaneous Expenses (Payment for Light and Water Bill of the Vaccination Venue) |  | 24000 |  |  |  | 37.2% | 8929 | 15071 |  | 15071 |  |  |  | x | [38 empty] | cx
18 | Rehabilitation of S. Lamanan, Sarayan-Pinamaton Rd. | MPDO/MEO | Brgy. Sarayan | 300000 |  |  |  | 100% | 299521.5 |  | 478.5 | Completed | [8 empty] | #DIV/0! |  | 0 |  | 0 |  |  |  | x | [38 empty] | cx
19 | Rehabilitation of N. Abra-N. Israel Rd. | MPDO/MEO | Brgy. N. Abra | 200000 |  |  |  | 0% | 0 |  | 200000 |  |  | 21 | Provision of Honorarium for Medical Doctor Attending to COVID-19 Vaccinees |  | 500000 |  |  |  | 99.6% | 498000 | 2000 |  | 2000 |  |  |  | x | [38 empty] | cx
| Sub-total (Economic) |  |  | 59900000 |  |  |  | 93.74% | 56147312.467 |  | 3752687.533 | [9 empty] | #DIV/0! |  | 0 |  | 0 |  |  |  | x | [38 empty] | cx
[14 empty] | 23 | Procurement of PPEs for COVID-19 Frontliners |  | 1500000 |  |  |  | 0% |  | 1500000 |  | 1500000 |  |  |  | x | [38 empty] | cx
C. | ENVIRONMENTAL MANAGEMENT(9000) | [12 empty] | 24 | Procurement of Rapid Testing Kits and Disinfectants for COVID-19 Response |  | 1000000 |  |  |  | 0% |  | 1000000 |  | 1000000 |  |  |  | x | [38 empty] | cx
1 | Solid Waste Management and SLF Operations | MMO/MENRO/MPDO |  | 989004 |  |  |  | 99.52% | 984237 |  | 4767 | Completed | [8 empty] | #DIV/0! |  | 0 |  | 0 |  |  |  | x | [38 empty] | cx
2 | National Greening Program | MMO/MENRO/MPDO |  | 300000 |  |  |  | 0% | 0 |  | 300000 |  |  |  | Provision of Food and Medicine Assistance to Quarantined Families due to COVID-19 | [7 empty] | 0 |  |  | Reprogrammed |  |  | x | [38 empty] | cx
| Sub-total (Environmental) |  |  | 1289004 |  |  |  | 76.36% | 984237 |  | 304767 |  |  |  | Sub-total (COVID-19 Vaccination Summary) |  | 8476675 |  |  |  |  | 5782604.65 | 2694070.35 |  | 2694070.35 | 68.22% |  |  | x
[29 empty] | x | [38 empty] | cx
| Grand Total |  |  | 66789004 |  |  |  | 85.69% | 57230412.467 |  | 9558591.533 |  |  | B. | ECONOMIC DEVELOPMENT (Infra-support) | [13 empty] | x | [38 empty] | cx
[14 empty] | 26 | Construction of F. Valdevieso Solar Dryer | Brgy. New Bugasong | 300000 |  |  |  | 76.32% | 228954 | 71046 |  | 71046 | 23.68% |  |  | x | [38 empty] | cx
| We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document. | [12 empty] | 27 | Construction of D. Almarines Solar Dryer | Brgy. Taguranao | 350000 |  |  |  | 97.63% | 341694 | 8306 |  | 8306 | Completed |  |  | x | [38 empty] | cx
[14 empty] | 28 | Construction of Kidama Solar Dryer | Brgy. Kidama | 300000 |  |  |  | 99.43% | 298282 | 1718 |  | 1718 | Completed |  |  | x | [38 empty] | cx
[14 empty] | 29 | Construction of Purok 2 Solar Dryer | Brgy. Manupal | 300000 |  |  |  | 75.01% | 225036.34 | 74963.66 |  | 74963.66 |  |  |  | x | [38 empty] | cx
| VIRGILIO M. FUERTE, MPA | [6 empty] | OSCAR M. VALDEVIESO | [5 empty] | 30 | Construction of Purok 1 Solar Dryer | Brgy. West Patadon | 300000 |  |  |  | 99.49% | 298462 | 1538 |  | 1538 | Completed |  |  | x | [38 empty] | cx
| Admin. Officer V/ OIC - Municipal Budget Officer | [6 empty] | Municipal Mayor | [5 empty] | 31 | Construction of Purok 4 Solar Dryer | Brgy. West Patadon | 300000 |  |  |  | 75.55% | 226662 | 73338 |  | 73338 |  |  |  | x | [38 empty] | cx
[14 empty] | 32 | Additional 370Ln.m. Concreting of Kibia-Latagan Road | Kibia-Latagan Road | 4100000 |  |  |  | 100% | 4089916.97 | 10083.03 |  | 10083.03 | Completed |  |  | x | [38 empty] | cx
[14 empty] | 33 | Additional 200Ln.m. Concreting of Linao-Bangbang via Kinilid Road | Brgy. Linao | 2700000 |  |  |  | 100% | 2694444.7 | 5555.3 |  | 5555.3 | Completed |  |  | x | [38 empty] | cx
[22 empty] | 0 | [6 empty] | x | [38 empty] | cx
[14 empty] | 34 | Concreting of 200 Ln.m. Central Malamote-SLF Road | Brgy. Central Malamote | 2200000 |  |  |  | 100% | 2192052.66 | 7947.34 |  | 7947.34 | Completed |  |  | x | [38 empty] | cx
[14 empty] | 35 | Concreting of 200 Ln.m. Dalapitan-New Pandan via Purok Bayabas Road | Brgy. New Pandan | 2200000 |  |  |  | 100% | 2192988.4 | 7011.6 |  | 7011.6 | Completed |  |  | x | [38 empty] | cx
[22 empty] | 0 | [6 empty] | x | [38 empty] | cx
[14 empty] | 36 | Concreting of 200 Ln.m. Central Malamote-Taculen Road | Brgy. Taculen | 2200000 |  |  |  | 100% | 2192855.23 | 7144.77 |  | 7144.77 | Completed |  |  | x | [38 empty] | cx
[13 empty] | cx | 37 | Additional Concreting of 250 Ln.m. Highway-Junction Pinamaton Road | Brgy. Pinamaton | 2800000 |  |  |  | 100% | 2794743.1305 | 5256.8695 |  | 5256.8695 | Completed |  |  | x | [38 empty] | cx
cx | cx |  | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | [9 empty] | 0 | [6 empty] | x | [38 empty] | cx
[14 empty] | 38 | Concreting of 400 Ln.m. Taguranao-Arakan Road | Brgy. Taguranao | 5500000 |  |  |  | 100% | 5492219 | 7781 |  | 7781 | Completed |  |  | x | [38 empty] | cx
[14 empty] | 39 | Concreting of 200 Ln.m. Lower Malamote-New Pandan Road | Brgy. Lower Malamote | 2250000 |  |  |  | 100% | 2242084.12 | 7915.88 |  | 7915.88 | Completed |  |  | x | [38 empty] | cx
[22 empty] | 0 | [6 empty] | x | [38 empty] | cx
[14 empty] | 40 | Loan Repayment to DBP |  | 25000000 |  |  |  | 96.78% | 24195739.1 | 804260.9 |  | 804260.9 |  |  |  | x | [38 empty] | cx
[15 empty] | Sub-total (Economic) |  | 50800000 |  |  |  |  | 49706133.6505 | 1093866.3495 |  | 1093866.3495 | 97.85% |  |  | x | [38 empty] | cx
[29 empty] | x | [38 empty] | cx
[14 empty] | C. | ENVIRONMENTAL MANAGEMENT(9000) | [13 empty] | x | [38 empty] | cx
[14 empty] | 41 | Aid to SLF Operation and Garbage Collections |  | 1000000 |  |  |  | 113.4% | 1133610 | -133610 |  | -133610 | Completed |  |  | x | [38 empty] | cx
[14 empty] | 42 | Support to Reforestation Program (National Greening and Earth Day) |  | 261629.6 |  |  |  | 0% | 0 | 261629.6 |  | 261629.6 |  |  |  | x | [38 empty] | cx
[15 empty] | Sub-total (Environmental) |  | 1261629.6 |  |  |  |  | 1133610 | 128019.6 |  | 128019.6 | 89.85% |  |  | x | [38 empty] | cx
[29 empty] | x | [38 empty] | cx
[14 empty] | D. | 2022 REPROGRAMMING | [13 empty] | x | [38 empty] | cx
[14 empty] | 1 | Support to COVID-19 Vaccination Program |  | 4000000 |  |  |  | 94.79% | 3791704 | 208296 |  | 208296 |  |  |  | x | [38 empty] | cx
[14 empty] | 2 | Rehabilitation of RHU Building used as Vaccination Center |  | 1500000 |  |  |  | 99.83% | 1497421.75 | 2578.25 |  | 2578.25 | Completed |  |  | x | [38 empty] | cx
[14 empty] | 3 | Construction of 3-Chamber COVID-19 Septic Vault |  | 500000 |  |  |  | 99.95% | 499757.5 | 242.5 |  | 242.5 | Completed |  |  | x | [38 empty] | cx
[14 empty] | 4 | Procurement of 6-Wheeler Mini-Dumptruck for Biodegradable Waste Collection |  | 1500000 |  |  |  |  | 1490000 | 10000 |  | 10000 | Completed |  |  | x | [38 empty] | cx
[14 empty] | 5 | Rehabilitation of Municipal Roads |  | 2500000 |  |  |  | 90.73% | 2268222.15 | 231777.85 |  | 231777.85 |  |  |  | x | [38 empty] | cx
[14 empty] | 6 | Concreting of Add'l 300LM Kibia-Latagan Rd, Natipakan Rd Section | Brgy. Kibia-Latagan | 5000000 |  |  |  | 99.93% | 4996540.4 | 3459.6 |  | 3459.6 | Completed |  |  | x | [38 empty] | cx
[15 empty] | Sub-total (2022 Reprogramming) |  | 15000000 |  |  |  |  | 14543645.8 | 456354.2 |  | 456354.2 | 96.96% |  |  | x | [38 empty] | cx
[27 empty] | 5 |  | x | [38 empty] | cx
[14 empty] | E. | 2018-2021 EDF BALANCES REPROGRAMMING | [11 empty] | 5 |  | x | [38 empty] | cx
[14 empty] | 1 | Palay Marketing Assistance Program for Legislators and LGUs | National Food Authority | 1000000 |  |  |  | 100% | 1000000 | 0 |  | 0 | Completed | 5 |  | x | [38 empty] | cx
[14 empty] | 2 | Rabies Vaccination Program |  | 560991.3 |  |  |  | 74.72% | 419160 | 141831.3 |  | 141831.3 |  | 5 |  | x | [38 empty] | cx
[29 empty] | x | [38 empty] | cx
[15 empty] | Sub-total |  | 1560991.3 |  |  |  |  | 1419160 | 141831.3 |  | 141831.3 | 90.91% |  |  | x | [38 empty] | cx
[29 empty] | x | [38 empty] | cx
[14 empty] | E. | CY 2018 20%EDF Balances | [13 empty] | x | [38 empty] | cx
[14 empty] | 1 | Reforestation/Procurement of Tree Planting Materials) | MENRO | 500000 |  |  |  | 5.981% | 29906 | 470094 | [5 empty] | x | [38 empty] | cx
[14 empty] | 2 | [14 empty] | x | [38 empty] | cx
[29 empty] | x | [38 empty] | cx
[15 empty] | Sub-total |  | 500000 |  |  |  |  | 29906 | 470094 | [5 empty] | x | [38 empty] | cx
[29 empty] | x | [38 empty] | cx
[29 empty] | x | [38 empty] | cx
[29 empty] | x | [38 empty] | cx
[29 empty] | x | [38 empty] | cx
[29 empty] | x | [38 empty] | cx
[29 empty] | x | [38 empty] | cx
[29 empty] | x | [38 empty] | cx
[29 empty] | x | [38 empty] | cx
[29 empty] | x | [38 empty] | cx
[15 empty] | Grand Total |  | 79649295.9 |  |  |  | 92.43% | 73618318.8505 | 9223634.099 |  | 4611817.0495 | 92.43% |  |  | x | [38 empty] | cx
[29 empty] | x | [38 empty] | cx
[13 empty] | cx |  | We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document. | [13 empty] | x | [38 empty] | cx
[29 empty] | x | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx
x
x
[15 empty] | SAMUEL F. FAELDONIA | [5 empty] | OSCAR M. VALDEVIESO | [7 empty] | x
[15 empty] | Municipal Budget Officer | [5 empty] | Municipal Mayor | [7 empty] | x
x
x
x
x
x
x
x
x
[14 empty] | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | x
Note on P5: RJGJ: