## 20%-2024
FDP Form 7-20% Component of the IRA Utilization
UTILIZATION OF THE 20% COMPONENT OF IRA FOR DEVELOPMENT PROJECTS (BUDGET YEAR 2024)
As of the 3rd Quarter, Calendar Year Ending December 31, 2024
REGION: XII - SOCCSKSARGEN CALENDAR YEAR: 2024
PROVINCE: COTABATO PROVINCE QUARTER: 3
CITY/MUNICIPALITY: MATALAM
| Program/Project/Activity | Implementing | Location | Total | Date Started | Target | Contract | Project Status |  | No. of | Balance
|  | Office/Dept. |  | Cost |  | Completion | Amount | % of | Total Cost | Extensions, |  | Remarks
[6 empty] | Date |  | Completion | Incurred to Date | if any |  | Completed
A. | SOCIAL DEVELOPMENT
1 | Procurement of Solar Powered Street Lights for the 34 Barangays of the Municipality | MPDO/MEO |  | 5440000 | 2024-06-06 | 2024-10-04 |  | 50% | 2414999.77 |  | 3025000.23 | In-Progress
2 | Const'n of 1-Unit Covered Court at Purok 2, Manubuan, Matalam, Cotabato | MPDO/MEO | Brgy. Manubuan | 3500000 | 2024-04-19 | 2024-09-26 |  | 51.26% | 1794159.7745 |  | 1705840.2255 | In-Progress
3 | Upgrading Additional Pipelines of PWS at Brgy. Bangbang, Matalam, Cotabato | MPDO/MEO | Brgy. Bangbang | 300000 |  |  |  | 0% | 0 |  | 300000
4 | Const'n of Solar Powered PWS at Purok Shalom, Brgy. Latagan, Matalam, Cotabato | MPDO/MEO | Brgy. Latagan | 500000 |  |  |  | 0% | 0 |  | 500000
5 | Upgrading of PWS at Brgy. Kabulacan, Matalam, Cotabato | MPDO/MEO | Brgy. Kabulacan | 300000 |  |  |  | 0% | 0 |  | 300000
6 | Const'n of PWS at Sitio Tuburan, Estado, Matalam, Cotabato | MPDO/MEO | Brgy. Estado | 300000 |  |  |  | 70.13% | 210400 |  | 89600
7 | Const'n of PWS (Additional Pipelines) and Reservoir at Pinamaton, Matalam, Cotabato | MPDO/MEO | Brgy. Pinamaton | 800000 |  |  |  | 87.44% | 699500 |  | 100500
8 | Upgrading of PWS at Sitio Maligaya (Solar Panel and Reservoir) at Brgy. Tamped, Matalam, Cotabato | MPDO/MEO | Brgy. Tamped | 800000 |  |  |  | 100% | 798000 |  | 2000 | COMPLETED
9 | Upgrading of PWS (Additional Pipelines) at Brgy. New Alimodian, Matalam, Cotabato | MPDO/MEO | Brgy. New Alimodian | 300000 |  |  |  | 0% | 0 |  | 300000
10 | Upgrading of PWS at Brgy. Estado, Matalam, Cotabato | MPDO/MEO | Brgy. Estado | 600000 |  |  |  | 0% | 0 |  | 600000
11 | Upgrading of PWS at Purok 2A, Brgy. Lampayan, Matalam, Cotabato | MPDO/MEO | Brgy. Lampayan | 300000 |  |  |  | 0% | 0 |  | 300000
12 | Improvement of Day Care Center at Brgy. Kibia, Matalam, Cotabato | MPDO/MEO | Brgy. Kibia | 300000 |  |  |  | 0% | 0 |  | 300000
13 | Improvement of Day Care Center at Brgy. Sitio Condring, Matalam, Cotabato | MPDO/MEO | Sitio Condring | 350000 |  |  |  | 75.08% | 262767 |  | 87233
14 | CSO/PWD Livelihood Projects at Brgy.Poblacion, Matalam, Cotabato | MPDO/MEO | Brgy. Poblacion | 150000 |  |  |  | 0% | 0 |  | 150000
15 | Support to Livelihood Projecys of Matalam Womens - Tsinelas Making | KALIPI Matalam |  | 150000 |  |  |  | 0% | 0 |  | 150000
16 | Const'n of Jeepney and Tricycle Terminal at Poblacion, Matalam, Cotabato | MPDO/MEO |  | 800000 |  |  |  | 0% | 0 |  | 800000
| Sub-total (Social Development) |  |  | 14890000 |  |  |  | 27.12% | 6179826.5445 |  | 8710173.4555
B. | ECONOMIC DEVELOPMENT (Infrastructure Programs)
1 | Const'n of 1-Unit Solar Dryer at Brgy. Bangbang, Matalam, Cotabato | MPDO/MEO | Brgy. Bangbang | 350000 |  |  |  | 74.21% | 259725 |  | 90275 | In-Progress
2 | Const'n of 1-Unit Solar Dryer at Purok 5, Brgy. Sarayan, Matalam, Cotabato | MPDO/MEO | Purok 5, Brgy. Sarayan | 350000 |  |  |  | 74.22% | 259785 |  | 90215 | In-Progress
3 | Const'n of 1-Unit Solar Dryer at Purok 4, Brgy. Sarayan, Matalam, Cotabato | MPDO/MEO | Purok 4, Brgy. Sarayan | 350000 | 2024-04-18 |  |  | 74.27% | 259935 |  | 90065 | In-Progress
4 | Const'n of 1-Unit Solar Dryer at Purok 6, Brgy. Kidama, Matalam, Cotabato | MPDO/MEO | Purok 6, Brgy. Kidama | 350000 |  |  |  | 0% | 0 |  | 350000
5 | Const'n of 1-Unit Solar Dryer at Brgy. Kidama Proper, Matalam, Cotabato | MPDO/MEO | Brgy. Kidama Proper | 300000 |  |  |  | 0% | 0 |  | 300000
6 | Const'n of 1-Unit Solar Dryer at Purok 5, Brgy. Lower Malamote, Matalam, Cotabato | MPDO/MEO | Purok 5, Brgy. L. Malamote | 300000 |  |  |  | 71.63% | 214897 |  | 85103 | In-Progress
7 | Const'n of 1-Unit Solar Dryer at Brgy. Pinamaton, Matalam, Cotabato | MPDO/MEO | Brgy. Pinamaton | 350000 |  |  |  | 74.22% | 259785 |  | 90215 | In-Progress
8 | Const'n of 1-Unit Solar Dryer at New Bacolod, Brgy. Minamaing, Matalam, Cotabato | MPDO/MEO | New Bacolod, Brgy. Minamaing | 350000 |  |  |  | 0% | 0 |  | 350000
9 | Concreting of Add'l 300LM Bangbang-Linao Road | MEO | Bangbang-Linao | 4800000 | 2024-02-19 | 2024-08-05 |  | 100% | 4793769.095 |  | 6230.905 | COMPLETED
10 | Concreting of 150LM Sitio Marva-A.M. Valdevieso Sr. School Road | MEO | S. Marva - Agustin M. Valdevieso Sr. School | 2500000 | 2024-02-19 | 2024-06-05 |  | 100% | 2497861.139 |  | 2138.861 | COMPLETED
11 | Concreting of 200LM Centro-Taguranao Road | MEO | Centro-Taguranao Road | 3400000 | 2024-02-19 | 2024-06-05 |  | 100% | 3397626.7475 |  | 2373.2525 | COMPLETED
12 | Concreting of 200LM Central Malamote-Taculen Road | MEO | Central Malamote - Taculen | 3000000 | 2024-02-19 | 2024-06-05 |  | 100% | 2994120.8865 |  | 5879.1135 | COMPLETED
13 | Concreting of 200LM New Pandan-Dalapitan via Patnungon Road | MEO | New Pandan-Dalapitan via Patnungon | 3000000 | 2024-02-19 | 2024-06-05 |  | 100% | 2997127.6085 |  | 2872.3915 | COMPLETED
14 | Concreting of 200LM Central Malamote-SLF Road | MEO | Central Malamote-SLF Road | 3000000 | 2024-02-19 | 2024-06-05 |  | 100% | 2994222.1755 |  | 5777.8245 | COMPLETED
15 | Concreting of 300LM Purok 1-Manupal Road | MEO | Purok 1-Manupal Road | 4200000 | 2024-02-19 | 2024-06-05 |  | 100% | 4193770.217 |  | 6229.783 | COMPLETED
16 | Rehabilitation of Sitio Kilomawa-Sitio Kibungkatot Road, Sarayan, Matalam, Cotabato | MEO | Brgy. Sarayan | 300000 | 2024-04-24 |  |  | 100% | 299603 |  | 397 | COMPLETED
17 | Rehabilitation of Sitio Migcuan-Sitio Eba Road, Sarayan, Matalam, Cotabato | MEO | Brgy. Sarayan | 300000 | 2024-04-24 |  |  | 100% | 299603 |  | 397 | COMPLETED
18 | Rehabilitation of Sitio Maiwag-Sitio Cogon Road, Sarayan, Matalam, Cotabato | MEO | Brgy. Sarayan | 500000 | 2024-04-24 |  |  | 100% | 499139 |  | 861 | COMPLETED
19 | Rehabilitation of Sitio Marva-Bato Road, Matalam, Cotabato | MEO | Sitio Marva-Bato Road | 500000 | 2024-04-24 |  |  | 96.58% | 482881.6 |  | 17118.4 | In-Progress
20 | Rehabilitation of Layangan-Bato Road, Matalam Cotabato | MEO | Layangan-Bato Road | 500000 |  |  |  | 0% | 0 |  | 500000
21 | Rehabilitation of Taguranao-Sitio Almarines Road, Matalam Cotabato | MEO | Taguranao-Sitio Almarines Road | 300000 |  |  |  | 100% | 299600 |  | 400 | COMPLETED
22 | Rehabilitationm of Cemetery Road, Taguranao, Matalam, Cotabato | MEO | Brgy. Taguranao | 200000 |  |  |  | 0% | 0 |  | 200000
23 | Road Opening of Sitio Dumahook-Sitio Maligaya Road, Tamped, Matalam, Cotabato | MEO | Sitio Dumahook-Sitio Maligaya Road | 500000 |  |  |  | 0% | 0 |  | 500000
24 | Road Opening: Sitio Malambog-Tamped Road, Matalam, Cotabato | MEO | Sitio Malambog-Tamped Road | 500000 |  |  |  | 97.4% | 486983 |  | 13017 | In-Progress
25 | Rehabilitation of Marbel-Estado Road, Matalam, Cotabato | MEO | Marbel-Estado Road | 300000 |  |  |  | 100% | 299800 |  | 200 | COMPLETED
26 | Rehabilitation of New Bacolod-Calora Road, Minamaing, Matalam, Cotabato | MEO | New Bacolod-Calora Road | 300000 |  |  |  | 0% | 0 |  | 300000
27 | Rehabilitation of Sitio Patnungon-Maligaya Road, New Pandan, Matalam, Cotabato | MEO | Sitio Patnungon-Maligaya Road, Brgy. New Pandan | 300000 |  |  |  | 100% | 299600 |  | 400 | COMPLETED
28 | Rehabilitation of Bubungan-Balabag Road, Linao, Matalam, Cotabato | MEO | Bubungan-Balabag Road, Brgy. Linao | 200000 |  |  |  | 0% | 0 |  | 200000
29 | Rehabilitation of New Abra-Israel Road, Matalam, Cotabato | MEO | New Abra-Israel Road | 300000 |  |  |  | 100% | 299800 |  | 200 | COMPLETED
30 | Rehabilitation of Purok Centro-Central Malamote Road, Matalam, Cotabato | MEO | Purok Centro-Central Malamote Road | 150000 |  |  |  | 100% | 149000 |  | 1000 | COMPLETED
31 | Rehabilitation of Sitio Kulog-Taguranao Road, Matalam, Cotabato | MEO | Sitio Kulog-Taguranao Road | 500000 |  |  |  | 0% | 0 |  | 500000 |  | cx
32 | Rehabilitation of Kidama-Kilada Road, Matalam, Cotabato | MEO | Kidama-Kilada Road | 200000 |  |  |  | 0% | 0 |  | 200000
33 | Rehabilitation of Sitio Ilomavis-Bubungan Road, Brgy Linao, Matalam, Cotabato | MEO | Sitio Ilomavis-Bubungan Road | 200000 |  |  |  | 0% | 0 |  | 200000
33 | Const'n of Linao (Malimit Creek) 2-Barrel Box Culvert, Matalam, Cotabato | MEO | Brgy. Linao | 3500000 |  |  |  | 100% | 3496364.69 |  | 3635.31 | COMPLETED
35 | Loan Repayment (Concreting of Roads, Matalam, Cotabato) | MTO |  | 18593209.8 |  |  |  | 90.41% | 16810850.55 |  | 1782359.25 | In-Progress
| Sub-Total (Economic Development) |  |  | 54743209.8 |  |  |  | 64.37% | 48845849.709 |  | 5897360.091
C. | ENVIRONMENTAL MANAGEMENT
1 | Solid Waste Management and Sanitary Land Fill Operations | MENRO |  | 1000000 |  |  |  | 81.68% | 816800 |  | 183200 | In-Progress
2 | National Greening Program | MENRO |  | 300000 |  |  |  | 0% | 0 |  | 300000
| Sub Total (Environmental Management) |  |  | 1300000 |  |  |  | 40.84% | 816800 |  | 483200
| Grand Total |  |  | 70933209.8 |  |  |  | 78.73% | 55842476.2535 |  | 15090733.5465
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
| VIRGILIO M. FUERTE, MPA | [6 empty] | OSCAR M. VALDEVIESO
| Municipal Budget Officer | [6 empty] | Municipal Mayor
cx | cx |  | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx
cx
cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx | cx